SOFTWARE DEVELOPMENT  PLAN (SDP) TEMPLATE

3 October 1997

Version 1.3

This page intentionally left blank

FOREWORD

This document was developed to provide any project developing software with a template for generating a Software Development Plan (SDP).  This template should be supplemented with project-specific information to produce an SDP that accurately describes the project’s organization, role, and responsibilities.  Space and Naval Warfare Systems Center’s (SSC San Diego) Software Project Planning Policy is SSC San Diego’s written organizational policy for implementing Software Project Planning (SPP) to provide management with appropriate visibility into the process being used by the software project and of the products being built.

This document is intended to supplement the SPP Process document by providing an SDP template that a project may use in generating their own project SDP.

This template describes the necessary elements to be considered when preparing an SDP.  The template  provides guidance and samples in the areas that are critical for the proper planning of a software project.

The SDP is the document that allows the customer  insight into all stages of the software development process and addresses the commitments  of the software developer to the allocated requirements.  It identifies resources, estimates of size and cost, schedules, constraints, capabilities of the software developer's organization.  The plan serves a basis for managing and tracking the software activities defined to accomplish the development of the project’s software.  The plan documents each group's responsibility for the development of the software.

The items contained in Performing General Software Development Activities, Section 4, identify basic topics which are necessary to create a workable plan for a software project.  When a significant change occurs in the approach to software development, this plan must be updated to reflect that change.  In addition, an SDP should be kept current by responding to changes due to programmatic redirection.

SSC San Diego’s Software Engineering Process Office (SEPO) will maintain keep this SDP Template. Users of this document may report deficiencies and or corrections using the format provided below attached Document Change Request (DCR) form.  SEPO will configuration manage this data as part of it’s process improvements to the SDP Template.

DOCUMENT CHANGE REQUEST (DCR)

DOCUMENT:______________________________________________________________

TRACKING NUMBER:_______

NAME OF SUBMITTING ORGANIZATION:_____________________________________

________________________________________________________________________

ORGANIZATION CONTACT:_________________________TELEPHONE:______________

MAILING ADDRESS:______________________________________________________

________________________________________________________________________

________________________________________________________________________

________________________________________________________________________

DATE:_______________SHORT TITLE:________________________________________

CHANGE LOCATION:_______________________________________________________

(use section #, figure #, table #, etc.)

PROPOSED CHANGE:

RATIONALE FOR CHANGE:

...............................................................................................................................................

Note:  For the Software Engineering Process Office (SEPO) to take appropriate action on a change request, please provide a clear description of the recommended change along with supporting rationale.

Send to:  SPAWARSYSCEN, SEPO, D13, 53560 Hull Street, San Diego, CA 92152-5001

or Fax to:  (619)553-6249

DCR Form 10/97

Administrative Information

Software Engineering Process Office, D13

Space and Naval Warfare Systems Center

53560 Hull Street, San Diego, CA  92152-5001

SOFTWARE DEVELOPMENT (SDP) PLAN TEMPLATE

Version 1.3

SEPO assumes responsibility for this document and updates it as required to meet the needs of users within SSC San Diego.  SEPO welcomes and solicits feedback from users of this document so that future revisions of this document will reflect improvements, based on organizational experience and lessons learned.

Approved for public release; distribution is unlimited.

Brian Groarke, SEPO, SSC San Diego

Voice:  (619)553-6248,  Fax:  (619)553-6249, Internet:  groarke@spawar.navy.mil

RECORD OF CHANGES

*A - ADDED  M - MODIFIED  D - DELETED

| CHANGE NUMBER | DATE | NUMBER OF FIGURE, TABLE OR PARAGRAPH | A* M D | TITLE OR BRIEF DESCRIPTION | CHANGE REQUEST NUMBER |
| --- | --- | --- | --- | --- | --- |
| 1 | 10/97 |  |  | Various changes resulting from Formal Inspection of this Document. |  |

TEMPLATE PROTOCOL

Background

This document provides a template for a generic Software Development Plan (SDP) that addresses the topics required by the Software Engineering Institute (SEI) Capability Maturity Model (CMM) Version 1.1 Level 2 “Repeatable Processes,” and MIL-STD-498.  The objective is to assist organizations in documenting software development processes in  support of the projects under their  cognizance.  Tailoring this template requires the author to address all requirements for the management, development, test, and coordination of those functional activities as necessary to delivering a quality product to the fleet.  In addition, the generic SDP employs a tailorable software development methodology.

Figure I-1 depicts the traditional practice of developing a sponsor-oriented, project-specific, SDP.  Often each of the SDPs describe different development methods, configuration practices and tools;  and quality assurance processes.

Figure I-1 Traditional Practice

For an organization, such as SSC San Diego, to achieve a level 3 of the SEI CMM it must embrace the associated 13 Key Process Areas (KPA)s.  One of those KPAs is Organization Process Definition (OPD).  The central theme of the OPD KPA is that an organization develop and maintain a repository of standard processes for use by its many projects.  To that end SEPO is employing its homepage as that repository for SSC San Diego, and populating that repository with SSC San Diego policies, standard processes, and key MIL-STD 498 document templates.

This  generic SDP Template, by taking its place in the repository, will assist in providing  the command a focus on a suite of standard mature processes.  In addition, it will help projects meet sponsor requirements for an SDP by providing quickly tailorable engineering processes.  Other templates available would include those for a Software Configuration Management Plan (SCMP) and a Software Quality Assurance Plan (SQAP).  Figure I-2 reflects the change in philosophy from a federation of sponsor driven processes to one of an organization employing standard processes.

Figure I-2  Process Oriented Organization

Document Conventions

Standard conventions are used within this document to assist the reader.  The outline of the SDP follows the requirements of MIL-STD-498 DID DI-IPSC-81427.  Each section of the outline contains a guidance box to assist the reader in drafting the content.

Guidance

The guidance box provides instructions and explanations, in italics, as required to assist the user in drafting their own information.

To further assist in drafting the required information many of the sections contain a sample formatted in the following manner.

[Sample]

The Software Project Manager is responsible for the overall conduct of the software development effort.

[End Sample]

The samples have been constructed such that if extracted from the template with their associate paragraph number they would create a good first draft of an SDP based on sound software engineering practices.

Users should first review the generic processes contained in the SDP to ensure an understanding of scope, software engineering processes, management functions, relationships, and responsibilities for the positions within the model organization.  For example, the samples address procedures for the positional roles contained in Section 7.1 of the SDP template.  A table is included in Section 7.1 as a Note to help define the roles in the model organization.  Throughout the samples the referenced positions are addressed in italics, as in the sample above, to assist in identification and substitution as required by the project during the tailoring of the supplied samples.  It is important to understand that the sample organization and processes do not fit all projects but serve as a representative example, requiring tailoring to meet project specific needs.

It is recommended that the Section 7.1 organizational diagram and table be printed and kept readily available for reference as one reads the individual samples associated with the guidance information.  The model organization and the processes contained template reflect a software project that is but one of several projects assigned to a Division.  The sample project is tasked to develop software; integrate it into its target hardware environment; support the software through the sponsor’s acceptance testing; and, provide distribution, field support, and follow-on maintenance.  It is also assumed that the Project Manager has established and placed in operation a System Configuration Control Board (SCCB).

Relationship to Other Documents

The SDP template contains software engineering process definitions and  references to other key templates for  software configuration management, and software quality assurance.  These companion documents also comply with MIL-STD-498 and its associated Data Item Descriptions (DIDs).  These templates comprise a suite of process descriptions that can be packaged in a multitude of formats.  The principal objective is to meet the SEI criteria of documenting processes and not necessarily to comply with a specific MIL-STD-498 DID format.  MIL-STD-498 was selected as it presents a widely recognized format and makes demands for SEI compliant processes at SEI CMM Level 2.

SOFTWARE DEVELOPMENT PLAN (SDP)

FOR THE

Project Name

Document Identifier

VERSION x.x

Prepared For:

Date

Prepared By:

Space and Naval Warfare Systems Center

(SSC San Diego)

Code Name, Code ####

Street Address

San Diego, CA 92152-####

Approved for public release; distribution is unlimited

SOFTWARE DEVELOPMENT PLAN (SDP)

FOR THE

Project Name

Document Identifier

VERSION x.x

Date

Prepared By:

Space and Naval Warfare Systems Center

(SSC San Diego)

Code Name, Code ####

Street Address

San Diego, CA 92152-####

Software Project Manager	Program Manager			Senior Manager

Configuration Management	Quality Assurance			Hardware Manager

Systems Engineer		Integrated Logistics Support		Test Manager

IV&V Activity		Facilities Manager			Other Affected Groups

RECORD OF CHANGES

*A - ADDED  M - MODIFIED  D - DELETED

| CHANGE NUMBER | DATE | NUMBER OF FIGURE, TABLE OR PARAGRAPH | A* M D | TITLE OR BRIEF DESCRIPTION | CHANGE REQUEST NUMBER |
| --- | --- | --- | --- | --- | --- |

TABLE OF CONTENTS

Section	 										Page

1. SCOPE

1.1 IDENTIFICATION

1.2 SYSTEM OVERVIEW

1.3 DOCUMENT OVERVIEW

1.4 RELATIONSHIP TO OTHER PLANS

2. REFERENCED DOCUMENTS

2.1 GOVERNMENT DOCUMENTS

2.1.1 Standards

2.1.2 Other Publications

2.2 NON-GOVERNMENT DOCUMENTS

2.2.1 Standards

3. OVERVIEW OF REQUIRED WORK

4. PLANS FOR PERFORMING GENERAL SOFTWARE DEVELOPMENT ACTIVITIES

4.1 SOFTWARE DEVELOPMENT PROCESS

4.2 GENERAL PLANS FOR SOFTWARE DEVELOPMENT

4.2.1 Software Development Methods

4.2.2 Standards for software products

4.2.3 Reusable Software Products

4.2.3.1 Incorporating Reusable Software Products

4.2.3.2 Developing Reusable Software Products

4.2.4 Handling of Critical Requirements

4.2.4.1 Safety Assurance

4.2.4.2 Security Assurance

4.2.4.3 Privacy Assurance

4.2.4.4

4.2.4.5 Assurance of Other Critical Requirements

4.2.5 Computer Hardware Resource Utilization

4.2.6 Recording of Rationale

4.2.7 Access for Acquirer Review

5. PLANS FOR PERFORMING DETAILED SOFTWARE DEVELOPMENT ACTIVITIES

5.1 PROJECT PLANNING AND OVERSIGHT

5.1.1 Software Development Planning

5.1.2 CSCI Test Planning

5.1.3 System Test Planning

5.1.4 Software Installation Planning

5.1.5 Software Transition Planning

5.1.6 Following and Updating Plans, including Intervals for Management Review

5.2 ESTABLISHING A SOFTWARE DEVELOPMENT ENVIRONMENT

5.2.1 Software Engineering Environment

5.2.2 Software Test Environment

5.2.3 Software Development Library

5.2.3.1 Document Library

5.2.3.2 Software Program Library

5.2.3.3 Correspondence & Reference Library

5.2.4 Software Development Files

5.2.4.1 Software Development File Approach

5.2.4.2 Software Development File Format

5.2.4.3 Software Development File Metrics

5.2.5 Non-deliverable Software

5.3 SYSTEM REQUIREMENTS ANALYSIS

5.3.1 Analysis of User Input

5.3.2 Operational Concept

5.3.3 System Requirements

5.4 SYSTEM DESIGN

5.4.1 System-Wide Design Decisions

5.4.2 System Architectural Design

5.5 SOFTWARE REQUIREMENTS ANALYSIS

5.5.1 Software Requirements Development Process

5.5.2 Software Requirements Change Process for Functional and Production Baselines

5.6 SOFTWARE DESIGN

5.6.1 CSCI-Wide Design Decisions

5.6.2 CSCI Architectural Design

5.6.2.1 Specify Architectural Model Process

5.6.2.2 Develop Class Categories/Classes/Operations

5.6.2.3 Map Software Requirements Process

5.6.2.4 Conduct Software Design Review Process

5.6.3 CSCI Detailed Design

5.6.3.1 Detailed Design Process

5.7 SOFTWARE IMPLEMENTATION AND UNIT TESTING

5.7.1 Software Implementation

5.7.1.1 Coding Process

5.7.1.2 Code Walkthrough Process

5.7.1.3 Software Development File Update

5.7.1.4 Support Tools

5.7.2 Preparing for Unit Testing

5.7.2.1 Unit Test Development

5.7.3 Performing Unit Testing

5.7.4 Revision and Retesting

5.7.5 Analyzing and Recording Unit Test Results

5.8 UNIT INTEGRATION AND TESTING

5.8.1 Preparing for Unit Integration and Testing

5.8.2 Performing Unit Integration and Testing

5.8.3 Revision and Retesting

5.8.4 Analyzing and Recording Unit Integration and Test Results

5.9 CSCI QUALIFICATION TESTING

5.9.1 Independence in CSCI Qualification Testing

5.9.2 Testing on the Target Computer System

5.9.3 Prepare for CSCI Qualification testing

5.9.3.1 Plan Software Tests Process

5.9.3.2 Develop Test Cases Process

5.9.3.3 Develop Test Procedures Process

5.9.3.4 Prepare Test Environment Process

5.9.3.5 Assure Readiness for Computer Software Configuration Item Qualification Testing

5.9.3.6 Conduct Test Readiness Review Process

5.9.4 Dry Run of CSCI Qualification Testing

5.9.5 Performing CSCI Qualification Testing

5.9.5.1 Execute Tests and Collect Data Process

5.9.6 Revision and Retesting

5.9.7 Analyze and Record CSCI Qualification Test Results

5.9.7.1 Analyze and Evaluate Results, Revise Tests Process

5.9.7.2 Report Test Results Process

5.10 CSCI/HWCI INTEGRATION AND TESTING

5.10.1 Preparing for CSCI/HWCI Integration and Testing

5.10.1.1 Plan Software Tests Process

5.10.1.2 Develop Test Cases Process

5.10.1.3 Develop Test Procedures Process

5.10.1.4 Prepare Test Environment Process

5.10.1.5 Assuring Readiness for Hardware Configuration Item/ Computer Software Configuration Item Integration and Testing

5.10.1.6 Conduct Test Readiness Review

5.10.2 Performing CSCI/HWCI Integration and Testing

5.10.3 Revision and Retesting

5.10.4 Analyzing and Recording CSCI/HWCI Integration and Test Results

5.10.4.1 Analyze and Evaluate Results, Revise Tests Process

5.10.4.2 Report Test Results Process

5.11 SYSTEM QUALIFICATION TESTING

5.11.1 Independence in System Qualification Testing

5.11.2 Testing on the Target Computer System

5.11.3 Preparing for System Qualification Testing

5.11.4 Dry Run of System Qualification Testing

5.11.5 Performing System Qualification Testing

5.11.6 Revision and Retesting

5.11.7 Analyzing and Recording System Qualification Test Results

5.12 PREPARING FOR SOFTWARE USE

5.12.1 Preparing the Executable Software

5.12.2 Preparing Version Descriptions for User Sites

5.12.3 Preparing User Manuals

5.12.3.1 Software User Manuals

5.12.4 Installation at User Sites

5.13 PREPARING FOR SOFTWARE TRANSITION

5.13.1 Preparing the Executable Software

5.13.2 Preparing Source Files

5.13.3 Preparing Version Descriptions for the Support Site

5.13.4 Preparing the “As Built” CSCI Design and Other Software Support Information

5.13.5 Updating the System Design Description

5.13.6 Preparing Support Manuals

5.13.6.1 Computer Programming Manuals

5.13.6.2 Firmware Support Manuals

5.13.7 Transition to the Designated Support Site

5.14 SOFTWARE CONFIGURATION MANAGEMENT

5.14.1 Configuration Identification

5.14.2 Configuration Control

5.14.3 Configuration Status Accounting

5.14.4 Configuration Audits

5.14.5 Packaging, Storage, Handling, and Delivery

5.15 SOFTWARE PRODUCT EVALUATION

5.15.1 In-process and Final Software Product Evaluations

5.15.2 Software Product Evaluation Records

5.15.3 Independence in Software Product Evaluation

5.16 SOFTWARE QUALITY ASSURANCE

5.16.1 Software Quality Assurance Evaluations

5.16.2 Software Quality Assurance Records

5.16.3 Independence in Software Quality Assurance

5.17 CORRECTIVE ACTION

5.17.1 Problem/Change Reports

5.17.2 Corrective Action System

5.18 JOINT TECHNICAL AND MANAGEMENT REVIEWS

5.18.1 Joint Technical Reviews

5.18.2 Joint Management Reviews

5.19 OTHER SOFTWARE DEVELOPMENT ACTIVITIES

5.19.1 Risk Management

5.19.2 Software Management Indicators

5.19.3 Security and Privacy

5.19.4 Subcontractor Management

5.19.5 Interface With Software Independent Verification and Validation (IV&V) Agents

5.19.6 Coordination With Associate Developers

5.19.7 Improvement of Project Processes

5.19.8 Other Activities

6. SCHEDULES AND ACTIVITY NETWORK

7. PROJECT ORGANIZATION AND RESOURCES

7.1 PROJECT ORGANIZATION

7.2 PROJECT RESOURCES

8. NOTES

8.1 ACRONYMS

9. APPENDIX A	A-

List of FIGURES/Tables

Section	 										Page

Table 3-1.  Key features of three DOD program strategies.

Table 4-1.  SEI CMM Processes

Table 4-2.   Standards and Specifications Applicable to Software Development

Table  5-1.  The XY Project SEE Tools

Table  5-2.  STE

Table  5-3.  XY Project's Non Deliverable Software

Table 7-1     Personnel Requirements (Person yrs)

This page intentionally left blank

# SCOPE

Guidance

The Software Development Plan (SDP) describes a developer’s plans for conducting a software development effort. The term "software development" is meant to include new development, modification, reuse, reengineering, maintenance, and all other activities resulting in software products. The SDP provides the acquirer insight into, and a tool for monitoring, the processes to be followed for software development, the methods to be used, the approach to be followed for each activity, and project schedules, organization, and resources.

## IDENTIFICATION

Guidance

This paragraph shall contain a full identification of the system and the software to which this document applies, including, as applicable, identification number(s), title(s), abbreviation(s), version number(s), and release number(s).

[SAMPLE]

This Software Development Plan (SDP)Software Development Plan (SDP) addresses planning for developing and integrating the software for XY Project.Common Data Link Management System (CDLMS).  Updates to this SDP will address future XY Project  software upgrades.

[END SAMPLE]

## SYSTEM OVERVIEW

Guidance

This paragraph shall briefly state the purpose of the system and the software to which this document applies. It shall describe the general nature of the system and software; summarize the history of system development, operation, and maintenance; identify the project sponsor, acquirer, user, developer, and support agencies; identify current and planned operating sites; and list other relevant documents.

## DOCUMENT OVERVIEW

Guidance

This paragraph summarizes the purpose and contents of this document.  The purpose is usually short enough for one paragraph of one to four sentences.  The contents of the various sections of this document are listed below:

Section 2 lists all the documents used as references during the preparation of this document as well as all documents referenced herein.

Section 3 enumerates the requirements that need to be imposed on developers in order for this plan to succeed.

Section 4 outlines the plans, methods, and processes to be employed by the Re-Engineering effort.

Section 5 provides the detail on the complete spectrum of software engineering activities being employed.

[SAMPLE]

This SDP identifies applicable policies, requirements, and standards for XY Project software development.  It defines schedules, organization, resources, and processes to be followed for all software activities necessary to accomplish the development.  This SDP contains no privacy considerations pertaining to the XY Project.

This SDP was developed in conformance with MIL-STD-498.  It is structured in sections following the format and content provisions of Data Item Description (DID)Data Item Description (DID) DI-IPSC-81427.  Each section identifies tailoring applied to the structure and instructions for content defined in the DID.

Section 2 lists all documents referenced by this SDP and used during its preparation.

Section 3 provides an overview of the required work.

Section 4 describes plans for general software development activities.

Section 5 describes the details of all software planning, design, development, reengineering, integration, test, evaluation, Software Configuration Management (SCM),Configuration Management (CM), product evaluation, Software Quality Assurance (SQA), and preparation for delivery activities.

Section 6 defines the project schedule and activity network.

Section 7 describes the project organization and the resources required to accomplish the work.

Section 8 contains the acronyms used in this SDP.

Appendices contain tabular resource planning tables, coding standards, and other pertinent forms and data.

[END SAMPLE]

## RELATIONSHIP TO OTHER PLANS

Guidance

This paragraph shall describe the relationship, if any, of the SDP to other project management plans.

[SAMPLE]

This SDP and its companion documents, the Software Configuration Management Plan (SCMP), and the Software Quality Assurance Plan (SQAP), serve as the guiding documents to develop the software for the XY Project.

[END SAMPLE]

# REFERENCED DOCUMENTS

Guidance

This section shall list the number, title, revision, and date of all documents referenced in this plan. This section shall also identify the source for all documents not available through normal Government stocking activities.

## GOVERNMENT DOCUMENTS

### Standards

Guidance

List  any r standards the developer is required to follow.

[SAMPLE]

a.  MIL-STD-498, Software Development and Documentation

b.  MIL-STD-1521, Technical Reviews and Audits for Systems, Equipments, and Computer Software

c.  Data Item Description DI-IPSC-81427, Software Development Plan

[END SAMPLE]

### Other Publications

[SAMPLE]

a.	SSC San Diego Software Project Planning Process

b.	SSC San Diego Software Development Plan Template

[END SAMPLE]

## NON-GOVERNMENT DOCUMENTS

### Standards

Guidance

List any non-Government standards, such as IEEE standards, the developer is required to follow.

# OVERVIEW OF REQUIRED WORK

Guidance

This section shall be divided into paragraphs as needed to establish the context for the planning described in later sections.  It shall include, as applicable:

a.  Requirements and constraints on the system and software to be developed

b.  Requirements and constraints on project documentation

c.  Position of the project in the system life cycle

d.  The selected program/acquisition strategy or any requirements or constraints on it

The three basic strategies are summarized below and in Table 3-1.

1.  Grand design. The "grand design" strategy (not named in DODI 5000.2 but treated as one strategy) is essentially a "once-through, do-each-step-once" strategy. Simplistically: determine user needs, define requirements, design the system, implement the system, test, fix, and deliver.

2.  Incremental. The "incremental" strategy (called "Preplanned Product Improvement" in DODI 5000.2) determines user needs and defines the system requirements, then performs the rest of the development in a sequence of builds. The first build incorporates part of the planned capabilities, the next build adds more capabilities, and so on, until the system is complete.

3.  Evolutionary. The "evolutionary" strategy (called "evolutionary" in DOD 5000.2) also develops a system in builds, but differs from the incremental strategy in acknowledging that the user need is not fully understood and all requirements cannot be defined up front. In this strategy, user needs and system requirements are partially defined up front, then are refined in each succeeding build.

e.  Requirements and constraints on project schedules and resources.

f.  Other requirements and constraints, such as project security, privacy, methods, standards, and interdependencies in hardware and software development.

| Program Strategy | Define All Requirements First? | Multiple Development Cycles? | Field Interim Software? |
| --- | --- | --- | --- |
| Grand Design | Yes | No | No |
| Incremental (Preplanned Product Improvement) | Yes | Yes | Maybe |
| Evolutionary | No | Yes | Yes |

Table 3-1.  Key features of three DOD program strategies.

This page intentionally left blank

# PLANS FOR PERFORMING GENERAL SOFTWARE DEVELOPMENT ACTIVITIES

Guidance

This section shall be divided into paragraphs  addressing the content specified in each sub header. Provisions corresponding to non-required activities may be satisfied by the words "Not applicable." If different builds or different software on the project require different planning, these differences shall be noted in the paragraphs.

In addition to the content specified below, each paragraph shall identify applicable risks/uncertainties and plans for dealing with them.

## SOFTWARE DEVELOPMENT PROCESS

Guidance

This paragraph shall describe the software development process to be used. The planning shall cover all contractual clauses concerning this topic, identifying planned builds, if applicable, their objectives, and the software development activities to be performed in each build.  Software development activities include:

a.  Project planning and oversight (5.1)

b.  Establishing a software development environment (5.2)

c.  System requirements analysis (5.3)

d.  System design (5.4)

e.  Software requirements analysis (5.5)

f.  Software design (5.6)

g.  Software implementation and unit testing (5.7)

h.  Unit integration and testing (5.8)

I.  CSCI qualification testing (5.9)

j.  CSCI/HWCI integration and testing (5.10)

k.  System qualification testing (5.11)

l.  Preparing for software use (5.12)

m.  Preparing for software transition (5.13)

n.  Integral processes:

1)	Software configuration management (5.14)

2) 	Software product evaluation (5.15)

3) 	Software quality assurance (5.16)

4)	Corrective action (5.17)

5)	Joint technical and management reviews (5.18)

6)	Other activities (5.19)

[SAMPLE]

The XY Project  software team will develop the system in accordance with processes defined in Section 5 in the context of the software engineering process model presented in figure 1.  The software development process is to construct an overall software architecture that will develop software in an incremental series of builds upon the chosen architecture.  The process will integrate reusable software from existing sources with newly-developed software.  Software design and coding will be performed by the Software Development Group using an object oriented design approach and generate class and object process interaction diagrams.  Artifacts and evidence of results of software development activities will be deposited in Software Development Files (SDFs)Software Development Files (SDFs) and Software Engineering Notebooks (SENs).Software Engineering Notebooks (SENs) These artifacts, along with pertinent project references will be deposited and maintained in a Software Development Library (SDL)Software Development Library (SDL) and made available to support management reviews, metrics calculations, quality audits, product evaluations, and preparation of product deliverables.

Following integration of reusable and new software units by the Software Test and Evaluation Group  a CSCI Formal Qualification Testing (FQT)Formal Qualification Testing (FQT) will be performed in accordance with processes defined in Section 5.  The Test Organization  will prepare an Software Test Plan (STP) and execute test cases defined in STDs.  They will generate STRs to describe results of test analyses.

Software Configuration Management (SCM),Software Configuration Management (SCM), Software Quality Assurance (SQA)Software Quality Assurance (SQA), and Software Product Evaluation, Corrective Action, and preparation for software delivery will follow detailed processes described in Section 5 of this SDP.

Figure 4-1 Software Engineering Process Model

[END SAMPLE]

## GENERAL PLANS FOR SOFTWARE DEVELOPMENT

[SAMPLE]

XY Project  software development will conform to MIL-STD-498.  The development approach will apply selected Level 2 and Level 3 software engineering processes in accordance with the Software Engineering Institute (SEI)Software Engineering Institute (SEI) Capability Maturity Model (CMM)Capability Maturity Model (CMM), and product evaluation procedures recommended by SSC San Diego’s Software Engineering Process Office (SEPO).Software Engineering Process Office (SEPO)  The project team has tailored these standards, practices, and processes to XY Project software development, as described in Section 5 of this SDP.  Table 4-1 lists the specific Level 2 and 3 processes to be applied to XY Project  software development.

Table 4-1.  SEI CMM Processes

| Software Process | SEI CMM Level |
| --- | --- |
| Requirements Management | Level 2 |
| Software Project Planning | Level 2 |
| Software Tracking and Oversight | Level 2 |
| Software Contractor Management | Level 2 |
| SQA | Level 2 |
| SCM | Level 2 |
| Organization Process Focus | Level 3 |
| Organization Process Definition | Level 3 |
| Software Product Engineering | Level 3 |
| Peer Reviews | Level 3 |

[END SAMPLE]

### Software Development Methods

Guidance

This paragraph shall describe or reference the software development methods to be used. Included shall be descriptions of the manual and automated tools and procedures to be used in support of these methods. The methods shall cover all contractual clauses concerning this topic. Reference may be made to other paragraphs in this plan if the methods are better described in context with the activities to which they will be applied.

[SAMPLE]

The XY  Project  software development will apply the following general methods:

- The project will follow the defined processes documented in Section 5 to conduct software requirements analysis and manage the Software Requirements Specification (SRS).  Express software requirements in language that addresses a single performance objective per statement and promotes measurable verification.  Construct a software architecture that will consist of reusable software components and components to be developed.  Allocate software requirements to one or more components of that architecture.  Use an automated data base tool to capture, cross-reference, trace, and document requirements.

- The project will follow the defined processes documented in Section 5 to conduct object-oriented top-level and detailed software design of new software and to capture the design, and reengineer if necessary the software to be reused.  Emphasis will be placed on good software engineering principles such as information hiding and encapsulation, providing a complete description of processing, and the definition of all software and hardware component interfaces to facilitate software integration and provide a basis for future growth.

- The project will follow only design and develop software to meet requirements that cannot be satisfied by reusable software.  New software will be based on principles of object-oriented design and exploit object-oriented features associated with the selected high-level language and development environment.  New software design will be defined at top-level and detailed design stages of development in the SDD.  Software design will promote ease of future growth, specifically new application interfaces. Top-level design will be expressed in a graphical form.  Detailed design will also be expressed in a graphical form depicting classes, relationships, operations, and attributes.

- The project will adhere to the standards required by the SDP for design and coding methods for new software.

- The project will reuse software for requirements that can be satisfied by selected Non-Development Item (NDI)Non-Development Item (NDI) software.  Since there may be limited documentation on the design of such software, the development method will involve reengineering the processing design from comments, source listings, users manuals, and hands-on verification of running software.  Software designers will select Commercial Off-The Shelf (COTS) Commercial Off-The Shelf (COTS) reengineering tools and methods best-suited to the structure of NDI software and host/target processors.  Reengineered design will be modified, as needed, to fully meet allocated requirements, and defined along with new software design, in the SDD.

- The project will modify (as necessary), unit test, integrate, and document reused software following the same processes used for new software.  While reused code will not be expected to conform to a single coding standard, changed source code must be supplemented with sufficient new comments and standard code headers to meet commenting provisions of the coding standard and to promote understandability

[END SAMPLE]

### Standards for software products

Guidance

This paragraph shall describe or reference the standards to be followed for representing requirements, design, code, test cases, test procedures, and test results. The standards shall cover all contractual clauses concerning this topic. Reference may be made to other paragraphs in this plan if the standards are better described in context with the activities to which they will be applied. Standards for code shall be provided for each programming language to be used. They shall include at a minimum:

a.  Standards for format (such as indentation, spacing, capitalization, and order of information)

b.  Standards for header comments (requiring, for example, name/identifier of the code; version identification; modification history; purpose; requirements and design decisions implemented; notes on the processing (such as algorithms used, assumptions, constraints, limitations, and side effects); and notes on the data (inputs, outputs, variables, data structures, etc.)

c.  Standards for other comments (such as required number and content expectations)

d.  Naming conventions for variables, parameters, packages, procedures, files, etc.

e.  Restrictions, if any, on the use of programming language constructs or features

f.  Restrictions, if any, on the complexity of code aggregates

[SAMPLE]

XY Project software development will comply with applicable directions contained in the documents listed in Table 4-2.  These documents impose standards that are applicable to software requirements, design, coding, testing, and data.

Table 4-2.   Standards and Specifications Applicable to Software Development

| Document | Description |
| --- | --- |
| <Fill in project specifics> | <Project programming standards are a good example.> |
| MIL-STD-498 | Software Development and Documentation, 5 December 1994 |
| MIL-STD-961D | DoD Standard Practice Defense Specifications |
| MIL-STD-973 | Configuration Management |
| Etc. |  |

[END SAMPLE]

### Reusable Software Products

[SAMPLE]

This section identifies and describes the planning associated with software reuse during development of the XY Project  and provisions to promote future reuse of newly-developed software.

[END SAMPLE]

#### Incorporating Reusable Software Products

Guidance

This paragraph shall describe the approach to be followed for identifying, evaluating, and incorporating reusable software products, including the scope of the search for such products and the criteria to be used for their evaluation. It shall cover all contractual clauses concerning this topic. Candidate or selected reusable software products known at the time this plan is prepared or updated shall be identified and described, together with benefits, drawbacks, and restrictions, as applicable, associated with their use.

Non-mandatory examples of specific criteria include, but are not limited to:

a. Ability to provide required capabilities and meet required constraints

b. Ability to provide required safety, security, and privacy

c. Reliability/maturity, as evidenced by established track record

d. Testability

e. Interoperability with other system and system-external elements

f. Fielding issues, including:

1) Restrictions on copying/distributing the software or documentation

2) License or other fees applicable to each copy

g. Maintainability, including:

1) Likelihood the software product will need to be changed

2) Feasibility of accomplishing that change

3) Availability and quality of documentation and source files

4) Likelihood that the current version will continue to be supported by the supplier

5) Impact on the system if the current version is not supported

6) The acquirer’s data rights to the software product

7) Warranties available

h. Short- and long-term cost impacts of using the software product

i. Technical, cost, and schedule risks and tradeoffs in using the software product

NOTE: Also refer to the SSC San Diego Reuse Adaptation and Management (RAM) Process - available on the SEPO home page.

#### Developing Reusable Software Products

Guidance

This paragraph shall describe the approach to be followed for identifying, evaluating, and reporting opportunities for developing reusable software products.

### Handling of Critical Requirements

Guidance

This paragraph shall be divided into the following subparagraphs to describe the approach to be followed for handling requirements designated critical.

#### Safety Assurance

Guidance

The developer shall identify as safety-critical those CSCIs or portions thereof whose failure could lead to a hazardous system state (one that could result in unintended death, injury, loss of property, or environmental harm).  If there is such software, the developer shall develop a safety assurance strategy, including both tests and analyses, to assure that the requirements, design, implementation, and operating procedures for the identified software minimize or eliminate the potential for hazardous conditions. The strategy shall include a software safety program, which shall be integrated with the system safety program if one exists.  The developer shall record the strategy in the software development plan, implement the strategy, and produce evidence, as part of required software products, that the safety assurance strategy has been carried out.

#### 4.2.4.2	Security Assurance

Guidance

The developer shall identify as security-critical those CSCIs or portions thereof whose failure could lead to a breach of system security. If there is such software, the developer shall develop a security assurance strategy to assure that the requirements, design, implementation, and operating procedures for the identified software minimize or eliminate the potential for breaches of system security. The developer shall record the strategy in the software development plan, implement the strategy, and produce evidence, as part of required software products, that the security assurance strategy has been carried out.

[SAMPLE]

XY Project  software will be subject to product evaluations, quality assurance, and test and evaluation activities conducted to assure that developed software meets the security requirements imposed by the following:

a. [Insert list of directives, guidance, etc.]

Software developers, integrators, and testers will adhere to security procedures to assure correct access to and handling of classified software, data, and documentation.  Security assurance procedures will be reviewed for compliance by the cognizant SSC San Diego security office.

[END SAMPLE]

#### Privacy Assurance

Guidance

The developer shall identify as privacy-critical those CSCIs or portions thereof whose failure could lead to a breach of system privacy.  If there is such software, the developer shall develop a privacy assurance strategy to assure that the requirements, design, implementation, and operating procedures for the identified software minimize or eliminate the potential for breaches of system privacy. The developer shall record the strategy in the software development plan, implement the strategy, and produce evidence, as part of required software products, that the privacy assurance strategy has been carried out.

#### Assurance of Other Critical Requirements

Guidance

If a system relies on software to satisfy other requirements deemed critical by the contract or by system specifications, the developer shall identify those CSCIs or portions thereof whose failure could lead to violation of those critical requirements; develop a strategy to assure that the requirements, design, implementation, and operating procedures for the identified software minimize or eliminate the potential for such violations; record the strategy in the software development plan; implement the strategy; and produce evidence, as part of required software products, that the assurance strategy has been carried out.

[SAMPLE]

Compatibility of interfaces with other systems is important in successful development of the XY Project  software.  These programs will be continually monitored by the Software Project Manager  to identify, track, and evaluate potential risks.

[END SAMPLE]

### Computer Hardware Resource Utilization

Guidance

This paragraph shall describe the approach to be followed for allocating computer hardware resources and monitoring their utilization.

[SAMPLE]

The Software Project Manager will establish and maintain a detailed schedule for computer hardware resource utilization that identifies anticipated users, purposes, and scheduled time to support analysis, software design, coding, integration, testing, and documentation.  It will address sharing of resources by multiple users and workarounds to resolve conflicts and equipment downtime.  If computer hardware resource scheduling requires supplementing, potential sources of computer hardware resources including other SSC San Diego projects or commercial vendors will be identified.  The Software Project Manager will coordinate resource needs with development, integration, and test groups.

[END SAMPLE]

### Recording of Rationale

Guidance

This paragraph shall describe the approach to be followed from recording rationale that will be useful to the support agency for key decisions made on the project.  It shall interpret the term "key decisions" for the project and state where the rationale are to be recorded.

[SAMPLE]

Software development processes for development of the XY Project software described in Section 5 of this SDP identify specific program decision information to be recorded.  Additional rationale required for software development will be provided in future SDP updates. Test management decisions and rationale will be recorded in the STP.

Decisions and rationale on software design, coding, and unit testing will be recorded in SDFs as well as the following:

-  System, software, and interface requirements

-  Software engineering, development, and test environments

-  System and CSCI test cases

[END SAMPLE]

### Access for Acquirer Review

Guidance

This paragraph shall describe the approach to be followed for providing the acquirer or its authorized representative access to developer and subcontractor facilities for review of software products and activities. It shall cover all contractual clauses concerning this topic.

[SAMPLE]

The Software Project Manager  will arrange for periodic reviews of XY Project software processes and products at appropriate intervals for the Project Manager.   The Software Project Manager will provide representatives of the Project Manager’s offices with electronic copies of briefing materials and draft products for review in advance of all reviews, along with discrepancy forms, in accordance with the project’s peer review process.   The Software Project Manager will direct consolidation of  discrepancies and report the status of corrective actions taken in response to reported discrepancies.

[END SAMPLE]

# PLANS FOR PERFORMING DETAILED SOFTWARE DEVELOPMENT ACTIVITIES

Guidance

This section shall be divided into paragraphs addressing the topics identified in the sub- headers. Provisions corresponding to non-required activities may be satisfied by the words "Not applicable."  If different builds or different software on the project require different planning, these differences shall be noted in the paragraphs.  The discussion of each activity shall include the approach (methods/procedures/tools) to be applied to: 1) the analysis or other technical tasks involved, 2) the recording of results, and 3) the preparation of associated deliverables, if applicable.  The discussion shall also identify applicable risks/uncertainties and plans for dealing with them.  Reference may be made to 4.2.1 if applicable methods are described there.

Note:  Several of the subparagraphs in section 5 contain detailed sample procedures.  These procedures could also be stand-alone documents that are merely referenced by the SDP.  Doing this makes the maintenance of the SDP easier because changes to there detailed procedures does not require an update of the SDP.

## PROJECT PLANNING AND OVERSIGHT

Guidance

This paragraph shall be divided into the following subparagraphs to describe the approach to be followed for project planning and oversight.  The planning in each subparagraph shall cover all contractual clauses regarding the identified topic.

[Sample]

This SDP shall be maintained and modified to reflect the current plans, policies, processes, resources, and standards affecting the XY Project.  It shall be the Software Project Manager’s responsibility to keep abreast of industry technology changes and programmatic direction from the Project Manager that would require modification of this plan.

[End Sample]

### Software Development Planning

Guidance

The developer shall develop and record plans for conducting the activities required by this standard and by other software-related requirements in the contract.  This planning shall be consistent with system-level planning and shall include all applicable items in the SDP.

Also refer to the SSC San Diego Software Project Planning (SPP) Process available on the SEPO home page.

[Sample]

The plan for all software development shall employ software engineering ‘best’ practices in verification and validation, CM, formal inspections, project tracking and oversight, and software quality assurance.  Microsoft Project will be used to develop and maintain the XY Project plans and schedules.  The project plans will be made available to all participants. The Software Project Manager  will use weekly project-wide meetings to maintain the status of the software project and to resolve any conflicts or changes that might occur.  The XY Project Software Project Manager will employ a database to record action item assignments, status’s, and resolutions.

[End Sample]

### CSCI Test Planning

Guidance

The developer shall develop and record plans for conducting CSCI qualification testing. This planning shall include all applicable items in the STP.

[Sample]

The XY Project consists of <N number of CSCIs>.  Test planning will be done for each of the components.  The XY Project CSCI components are: <list>.

There will be a common SRS for each CSCI component, allowing each to proceed through the life cycle phases independently until integration.  Planning for and conducting the individual CSCI component testing is the responsibility of the Software Development Manager and the Software Test and Evaluation Manager.  Test procedures will be devised for each respective set of CSCI component requirements in the SRS.  The intent is to validate that the XY Project CSCI components individually meet their SRS and Interface Requirements Specification(IRS)/Interface Design Document (IDD)Interface Design Document (IDD) requirements and that the XY Project CSCI components taken as a system meet the performance requirements of the SRS.  Paragraph 5.9 documents the processes for software test planning, test case construction, test procedure development, conduct, results analysis, and reporting.

[End Sample]

### System Test Planning

Guidance

The developer shall participate in developing and recording plans for conducting system qualification testing. For software systems, this planning shall include all applicable items in the Software Test Plan (STP) DID. (The intent for software systems is a single software test plan covering both CSCI and system qualification testing.)

[Sample]

The intent of system test planning is to validate that XY Project as a system meets its performance requirements.  It will be the responsibility of the System Test  Manager to direct the development of system test plans and procedures based on  System/Subsystem Specification (SSS), and conduct the system tests.  Paragraph 5.11 documents the processes for system test planning, test case construction, test procedure development, conduct, results analysis, reporting and participation of the Software Test and Evaluation Group.  The System Test Group will prepare STRs to document the results of the XY Project testing.

[End Sample]

### Software Installation Planning

Guidance

The developer shall develop and record plans for performing software installation and training at the user sites specified in the contract. This planning shall include all applicable items in the Software Installation Plan (SIP).

[Sample]

Software installation is at the direction of the Project Manager and will be performed according to the procedures established in  paragraph 5.12 of this SDP.

[End Sample]

### Software Transition Planning

Guidance

The developer shall identify all software development resources that will be needed by the support agency to fulfill the required support. The developer shall develop and record plans identifying these resources and describing the approach to be followed for transitioning deliverable items to the support agency.  This planning shall include all applicable items in the Software Transition Plan (STrP) DID.

Also refer to the SSC San Diego Software Transition Plan (STrP) Template available on the SEPO home page.

[Sample]

The XY Project  will remain at SSC San Diego for Life Cycle Maintenance (LCM); therefore, there is no need to identify a transition process.  This paragraph has been tailored out.

[End Sample]

### Following and Updating Plans, including Intervals for Management Review

Guidance

Following acquirer approval of any of the plans in this section, the developer shall conduct the relevant activities in accordance with the plan. The developer’s management shall review the software development process at intervals specified in the software development plan to assure that the process complies with the contract and adheres to the plans. With the exception of developer-internal scheduling and related staffing information, updates to plans shall be subject to acquirer approval.

[Sample]

The  Software Project Manager will monitor adherence to project plans and processes and will meet quarterly with the Project Manager’s office to review progress and plan changes. The Software Project Manager will act as the agent to effect changes in plans, schedules and direction as mandated by the management team.  The Software Project Manager will supply monthly reports on project metrics.

[End Sample]

## ESTABLISHING A SOFTWARE DEVELOPMENT ENVIRONMENT

Guidance

The developer shall establish a software development environment in accordance with the  requirement specified in Section 5.2.  Note: If a system or CSCI is developed in multiple builds, establishing the software development environment in each build should be interpreted to mean establishing the environment needed to complete that build.

[Sample]

These paragraphs describe the approach to establish and maintain the physical resources used to develop and deliver the XY Project software.

[End Sample]

### Software Engineering Environment

Guidance

The developer shall establish, control, and maintain a software engineering environment to perform the software engineering effort. The developer shall ensure that each element of the environment performs its intended functions.

[Sample]

The  XY Project hardware/software development and integration will take place at SSC San Diego.  The initial phase of software development will take place in <Bldg X>, while the hardware integration will take place at < Bldg Y>.  Only one Software Engineering Environment (SEE) will be developed and it will be physically located at SSC San Diego.

Table 5-1 provides the SEE tool sets that will be used on the program.

Table  5-1.  The XY Project SEE Tools

| Product | Tool(s) |
| --- | --- |
| Development | <identify compiler, test tools, etc.> |
| Project Schedule | <Microsoft Project> |
| Configuration Management | <Revision Control System (RCS) etc. Revision Control System (RCS) |
| Documentation | <Microsoft Word/Microsoft Excel> |

<Modify and expand as necessary>

[End Sample]

### Software Test Environment

Guidance

The developer shall establish, control, and maintain a software test environment to perform qualification, and possibly other, testing of software. The developer shall ensure that each element of the environment performs its intended functions.

[Sample]

The Software Test Environment (STE) Software Test Environment (STE)for the XY Project will be housed at <Bldg Y>.  Many STE components will be the same as for the Software Engineering Environment (SEE).  Table 5-2 provides the equipments to be used in the STE.

Table  5-2.  STE

| Nomenclature | Equipment | Quantity Required | Purpose |
| --- | --- | --- | --- |
| STE Primary Connectivity |  |  |  |
| XY Project Processor |  | 1 | Host XY Project software |

<Modify and expand as necessary>

[End Sample]

### Software Development Library

Guidance

The developer shall establish, control, and maintain a Software Development Library (SDL) to facilitate the orderly development and subsequent support of software. The SDL may be an integral part of the software engineering and test environments.  The developer shall maintain the SDL for the duration of the contract.

Also refer to the SSC San Diego Software Development Library (SDL) Template available on the SEPO home page.

[Sample]

The Software Development Library (SDL) is the master library of all programs, documents, reports, manuals, specifications, reference documents, and correspondence associated with the XY Project. The SCM Manager functions as the Software Librarian.

The SCM Manager controls the Software Development Files  (SDFs), the records/minutes of formal reviews, and the Change Control Documents.  The SDF is the control and tracking document for software components during all phases of the software development process.  The Change Control Documents include the Problem/Change Report (P/CR) and the Review and Response (R&R)Review and Response (R&R) Form.

The SCM Manager will produce the XY Project Master Document Status Summary and the Change Control Document Status Summary.  For administrative purposes, the SDL is subdivided into three distinct libraries:  Document, Program, and Correspondence & Reference.  The  XY Project Software Development Library is located at SSC San Diego.  The  XY Project Software Project Manager and SCM Manager will maintain control over all their software support items.

#### Document Library

The  Document Library, located in  <Bldg X>,  consists of all specifications, manuals, documents, and reports directly related to XY Project software.  The associated P/CRs, SDFs, Document R&R Forms, and the records/minutes of the formal reviews and other formal project meetings are included.

Documents approved for baseline by the  XY Project Software Project Manager will be given to the SCM Manager for Configuration Control (CC).Configuration Control (CC).  The SCM Manager will be responsible for the preparation of the cover and title pages with appropriate signatures and the List of Effective Pages.  Both machine (magnetic) and hard (paper) copy will be maintained in the Document Library.  Upon receipt of changes to baseline documents, the Software Project Manager will ensure that the change is reviewed for completeness, accuracy, and form.  When discrepancies are found, the change will be returned to the change originator for correction or resolution of the discrepancy.  Upon approval of changes by the XY Project Software Project Manager, the SCM Manager will make changes to the baseline document and print a hard copy.

Clearly labeled drafts and preliminary iterations of XY Project documents may be placed in the Document Library at the discretion of the Software Project Manager until such documents are readied for baselining.  These documents may include technical, operations, maintenance, and specification manuals.  Once baselined, all preliminary or draft issues will be disposed of as directed by the XY Project Software Project Manager.  All updates and subsequent issues of documents must be maintained in the Document Library.  Only current editions will be filed.

Document R&R Forms are maintained in the Document Library.  A copy of Quality Assurance (QA)Quality Assurance (QA) review comments will be held in a file until responses are received and signed.  The signed R&R forms will then be filed and may not be removed from the library.  Working copies may be requested from the SCM Manager.  All test Reports will be maintained in the Document Library.  The originals will not be removed from the library.  Copies may be requested from the SCM Manager.

Classified documents will be handled in accordance with the Navy Security Manual, Executive Order 12958, OPNAVINST 5510.1H, and DoD 5220.22-M.

#### Software Program Library

The Software Program Library is located in <Bldg X>, XY Project development sight.  The library consists of program disks and listings of programs that are under development and are being maintained in the SDL until delivered as a program package.  Programs or program changes under development will be maintained by the XY Project Software Development Group.  Once ready for baselining, program modules are entered into the Program Library only by the SCM Manager.  These procedures are subject to monitoring by the SQA Group’s activities.

#### Correspondence & Reference Library

The XY Project  has its Reference Library located at <Bldg X> and consists of hardware technical manuals, military standards, specifications, and instructions.  It also consists of XY Project memoranda, documents, and deliverables related to the XY Project.  Reference manuals and documents are categorized and filed by their military identification number.  Classified materials are handled in accordance with the Navy Security Manual, Executive Order 12958, OPNAVINST 5510.1H, and DoD 5220.22-M.  Only correspondence and items approved by the XY Project Software Project Manager are accepted by the SCM Manager for inclusion in the Correspondence Library.  Correspondence will be identified by originator, originator serial number, date of origination, and subject matter.

[End Sample]

### Software Development Files

Guidance

The developer shall establish, control, and maintain a SDF for each software unit or logically related group of Software Unit (SU)s, for each CSC, and, as applicable, for logical groups of CSCIs, for subsystems, and for the overall system. The developer shall record information about the development of the software in appropriate SDFs.

For additional information refer to the SSC San Diego Software Development File (SDF) Template available on the SEPO home page.

[Sample]

SDFs will provide visibility into the development status of XY Project.  The Software Development Group will maintain SDFs for each SU or collection of  SUs that make up a CSCI and/or XY Project component.  SDFs will be the principal working logs for assigned programmers.  The Software Development Group will maintain SDFs primarily on electronic media and periodically ensure the completeness, consistency, and accuracy of SDFs with respect to specifications, design, and user manuals.

SDFs will provide:

- An orderly repository for information essential to SU development and unit testing

- Management visibility into software development progress

- Recording of design/implementation decisions and rationale

- The Software Development Group will organize SDFs to contain the following information:

(1)  	Introduction - Statement of purpose and objectives, lists the contents of the SDF

(2)  Requirements - SU allocated requirements with a cross reference and pertinent programmer notes

(3)  	Design Data - Schedules, Status, CSCI, and SU design in the design depiction method selected for the CSCI

(4)  	Source Code - Contains listings, by directory, of SU source code files

(5)  	Test Plan and Procedures - Current unit test plan and procedures (for SUs). Integration plans and procedures (for CSCIs)

(6)  	Test Reports - Unit (for SUs) and integration (for CSCIs) test results and reports

(7)  	Review and Audit Comments - Record of  reviews and sign-off signatures resulting from reviews and informal audits

#### Software Development File Approach

At the beginning of the software planning phase, an SDF will be created for each CSCI.  During the high-level design (architecture) portion of the software design phase, the CSCI is broken down into high-level SUs, and SDFs are created for each SU identified.  As the design progresses, high-level components are decomposed into sublevel SUs, and additional SDFs are created for each SU.

SDFs will be maintained by the  Software Configuration Control Manager and will be periodically audited by the Software Development Manager and SQA Group. With the exception of metrics, each programmer is responsible for submitting all material and information required for preparation and maintenance of the SDFs.

#### Software Development File Format

In the front of each SDF is a task tracking sheet that contains schedules and actual dates of development milestones for the software component.  The SDF contains sections applicable to each phase of the development of the software component.  Each section of the SDF begins with a header that identifies the phase, software component, and the contract.  Each section contains metrics data, schedules, and phase-specific data such as interfaces or specification paragraph references.  The SCM Manager will maintain the SDF database with input from responsible engineers.

#### Software Development File Metrics

The collection of metrics is performed in each software development phase.  All estimates and actuals will be recorded in the SDFs by the Software Configuration Control Manager.  This database will be the basis for metrics estimation analysis at the end of each development phase and at project end.

[End Sample]

### Non-deliverable Software

Guidance

The developer may use non-deliverable software in the development of deliverable software as long as the operation and support of the deliverable software after delivery to the acquirer do not depend on the non-deliverable software or provision is made to ensure that the acquirer has or can obtain the same software. The developer shall ensure that all non-deliverable software used on the project performs its intended functions.

[Sample]

Non-deliverable software shall consist of all the software that is not specifically required to be delivered, but is used in the design, development, manufacture, inspection, or test of deliverable products.  It may include but not limited to:

- Software used to design or support the design of a deliverable product which may include databases, design analysis, modeling, simulation, digitizers, and graphic plotters

- Software used for in-process testing of deliverable products, or to generate input data or acceptance criteria data for the test program

Non-deliverable software for  the XY Project is listed in Table 5-3.

Table  5-3.  XY Project's Non Deliverable Software

| Description | Development Phase | Source | Purpose |
| --- | --- | --- | --- |

<Expand table as necessary>

[End Sample]

## SYSTEM REQUIREMENTS ANALYSIS

Guidance

This paragraph shall describe the approach to be followed for participating in system requirements analysis.

Note: If a system is developed in multiple builds, its requirements may not be fully defined until the final build. The developer’s planning should identify the subset of system requirements to be defined in each build and the subset to be implemented in each build.  System requirements analysis for a given build should be interpreted to mean defining the system requirements so identified for that build.

Also refer to the Requirements Management (RM) Guidebook.

[Sample]

The Software Configuration Control Group will process requests for clarification, change, and waiver/deviation in accordance with SCM procedures defined in Software Configuration Management Plan (SCMP).  The Software Project Manager will convene a Local Software Configuration Control Board (LCCB)Software Configuration Control Board (SCCB). to direct revision of baselined documents, review changes for the SSS, and submit approved change requests as ECPs to System Configuration Control Board (SCCB) for final approval.

[End Sample]

### Analysis of User Input

Guidance

The developer shall participate in analyzing user input provided by the acquirer to gain an understanding of user needs. This input may take the form of need statements, surveys, problem/change reports, feedback on prototypes, interviews, or other user input or feedback.

[Sample]

The Software Project Manager, acting as Chair of the LCCB, will assign candidate requests to the  Software Development Group for analysis of their impact on requirements documents.  The Software Development Group will process requests and prepare recommendations for the LCCB as follows:

- Requests for clarification will be evaluated to determine if one or more requirements need to be reworded.  If a clarification requires a change to a requirement, it will be processed as a request for change.

- Requests and rationale for change will be evaluated with respect to the status of software development to determine the impact on schedule, effort, and cost for software requirements analysis, design, implementation, integration, and testing.

- Requests and supporting rationale for waiver/deviation of requirements will be evaluated with respect to their impact on the overall processing integrity of XY Project.

[End Sample]

### Operational Concept

Guidance

The developer shall participate in defining and recording the operational concept for the system. The result shall include all applicable items in the Operational Concept Description (OCD) DID.

[Sample]

The LCCB will analyze requests for clarification, change, or waiver/deviation that impact the OCD, and/or SSS and prepare an impact assessment. They will evaluate constraints imposed by such factors as interfacing systems, system architecture, NDI software selections, and hardware capabilities and forward them to the sponsor for action.  Changes impacting the OCD and/or SSS will be forwarded with supporting material to the SCCB for consideration.

[End Sample]

### System Requirements

Guidance

The developer shall participate in defining and recording the requirements to be met by the system and the methods to be used to ensure that each requirement has been met. The result shall include all applicable items in the System/Subsystem Specification (SSS) DID.   Requirements concerning system interfaces may be included in the SSS or in interface requirements specifications (IRSs).

Note: If a system consists of subsystems, the activity in 5.3.3 is intended to be performed iteratively with the activities in 5.4 (System design) to define system requirements, design the system and identify its subsystems, define the requirements for those subsystems, design the subsystems and identify their components, and so on.

[Sample]

The SCCB  in the Project Manager’s office will control documents constituting the system requirements baseline; respond to requests for clarification, correction, or waivers/deviations; analyze impacts; revise the OCD and SSS; record system requirements measures; and manage the system requirements change process.

[End Sample]

## SYSTEM DESIGN

Guidance

This paragraph shall be divided into the following subparagraphs to describe the approach to be followed for participating in system design.

Note: If a system is developed in multiple builds, its design may not be fully defined until the final build. The developer’s planning should identify the portion of the system design to be

defined in each build. System design for a given build should be interpreted to mean defining the portion of the system design identified for that build.

### System-Wide Design Decisions

Guidance

The developer shall participate in defining and recording system-wide design decisions (that is, decisions about the system’s behavioral design and other decisions affecting the selection and design of system components). The result shall include all applicable items in the system-wide design section of the System/Subsystem Design Description (SSDD).   Design pertaining to interfaces may be included in the SSDD or in interface design descriptions (IDDs) and design pertaining to databases may be included in the SSDD or in database design descriptions (DBDDs).

Note: Design decisions remain at the discretion of the developer unless formally converted to requirements. The developer is responsible for fulfilling all requirements and demonstrating this fulfillment through qualification testing (see 5.9, 5.11).  Design decisions act as developer-internal "requirements" to be implemented, imposed on subcontractors, if applicable, and confirmed by developer-internal testing, but their fulfillment need not be demonstrated to the acquirer.

### System Architectural Design

Guidance

The developer shall participate in defining and recording the architectural design of the system (identifying the components of the system, their interfaces, and a concept of execution among them) and the traceability between the system components and system requirements. The result shall include all applicable items in the architectural design and traceability sections of the System/Subsystem Design Description (SSDD). Design pertaining to interfaces may be included in the SSDD or in interface design descriptions (IDDs).

## SOFTWARE REQUIREMENTS ANALYSIS

Guidance

This paragraph shall describe the approach to be followed for software requirements analysis.

The developer shall define and record the software requirements to be met by each CSCI, the methods to be used to ensure that each requirement has been met, and the traceability between the CSCI requirements and system requirements.  The result shall include all applicable items in the SRS.  The requirements concerning CSCI interfaces may be included in SRSs or in IRSs.

Note: If a CSCI is developed in multiple builds, its requirements may not be fully defined until the final build. The developer’s planning should identify the subset of each CSCI’s requirements to be defined in each build and the subset to be implemented in each build.  Software requirements analysis for a given build should be interpreted to mean defining the CSCI requirements so identified for that build.

Also refer to the Requirements Management (RM) Guidebook available on the SEPO home page.

[Sample]

The software requirements for XY Project are allocated from the SSS by the Systems Engineering Group.  The Software Project Manager  will apply the following process to develop, document, and manage software requirements for the XY Project.

### Software Requirements Development Process

The purpose of  Software Requirements Analysis process is to formulate, document, and manage the software performance baseline; respond to requests for clarification, correction, or waivers/deviations; analyze impacts; revise the SRS as directed; record software requirements measures; and manage the requirements analysis and change process.

ENTRY CRITERIA:

-	Software baselines under control

PRINCIPAL:  Software Requirements Team

ACTIVITIES:

- Attribute in a database the system requirements allocated to software to the level of detail needed to describe the systems software capabilities

- Produce the first draft of the SRS.  Perform Preliminary analysis of document

- Provide a traceability matrix between the SSS and the SRS

- Document the qualification procedures for each of the software requirements and enter into the Data Base.  Create hard copy report to be used as an appendix to SRS

- Produce the preliminary draft of the SRS.   Distribute for analysis and comment

- Members of the SQA Group and IV&V  Group provide analysis and Design Review (DR) comments

- The Software Project Manager will direct a requirements review to ensure that the SRS meets the system requirements allocated to software, the scope is consistent with the budget and the schedule, and obtains approval of the SRS by the Project Manager

- Publish the SRS and commence LCM of SRS

EXIT CRITERIA:

-	SRS signed

-	Requirements attributed and quantified in a database

### Software Requirements Change Process for Functional and Production Baselines

The purpose of the Software Requirements Change process is to control the software requirements baseline; respond to requests for clarification, correction, or waivers; revise the SRS; and manage the change process.  When the SCCB directs changes to the SRS via an approved ECP/SCN, the Software Requirements Team will prepare revised change pages in accordance with the Software Requirements Change Process. Changes affecting the SSS will also be submitted to the SCCB where the System Requirements Change process  will take precedence.

ENTRY CRITERIA:

-	Baselined SRS

-	XY Project SCCB established by the acquiring agency

-	Local Software CCB established

PRINCIPAL:  Software Requirements Team

ACTIVITIES:

- Receive, log, and process proposed requirements changes and requests for clarification, correction, or waiver/deviation.

- Analyze relationships between proposed changes and baselined requirements.

- Define results of change evaluations and estimate effort to implement changes in requirements baseline.  Record results of evaluations on approved forms.

- Recommend responses to requests for clarification or waiver/deviation to LCCB on appropriate forms.

- The LCCB verifies defined requirements changes/corrections, clarifications, and recommended responses to requests for waivers/deviations.

- The LCCB  approve or reject proposed changes and corrections in requirements baseline, clarifications, or responses to waiver/deviation requests.  Forwards changes impacting the SSS to the SCCB.

- Incorporate approved changes/corrections in SRS sections and modify requirements entries in the requirements database.  Revise the requirements count.

- Re-baseline modified SRS.  Develop Configuration Status Accounting Report (CSAR) for re-baselined document, document results of analyses and LCCB actions, and record the number of requests processed.

EXIT CRITERIA:

-	SRS rebaselined, if necessary

-	Clarifications, corrections, and responses to requests for waiver/deviation completed

-	Number of change requests received, approved, or rejected recorded

-	Revised number of requirements recorded

[End Sample]

## SOFTWARE DESIGN

Guidance

This paragraph shall be divided into the following subparagraphs to describe the approach to be followed for software design. The planning in each subparagraph shall cover all contractual clauses regarding the identified topic.

Note: If a CSCI is developed in multiple builds, its design may not be fully defined until the final build. Software design in each build should be interpreted to mean the design necessary to meet the CSCI requirements to be implemented in that build.

Also refer to the SSC San Diego Object-Oriented Design (OOD) process (available on the SEPO home page) if you are using object-oriented design.

[Sample]

The software design approach for the XY Project will be Object-Oriented Design (OOD).   The methodology, definition of terms, and notation for new software design will be based on the Booch Method for OOD.  This section describes the software design process and the artifacts produced by this process.

Software design will occur incrementally.  A top-level design for XY Project software will be developed during the preliminary design phase.  During the detailed design phase, the software necessary to meet the capabilities assigned to XY Project incremental builds will undergo detailed design to a level sufficient for implementation in support of targeted capabilities.

A software architectural model of XY Project will be placed under developmental configuration management following the top-level design review.  Updates and refinements to the model will occur incrementally during detailed design.  An updated model will be placed under developmental configuration management following each successful Detailed Design Review (DDR).

The design step produces a data design, an updated architectural design, and a procedural design.  The data design transforms the information model created during analysis into the data structures that will be required to implement the software.  The procedural design transforms the functional model into a procedural description of the software.

[End Sample]

### CSCI-Wide Design Decisions

Guidance

The developer shall define and record CSCI-wide design decisions (that is, decisions about the CSCI’s behavioral design and other decisions affecting the selection and design of the SUs comprising the CSCI. The result shall include all applicable items in the CSCI-wide design section of the SDD. Design pertaining to interfaces may be included in SDDs or in IDDs and design pertaining to databases may be included in SDDs or DBDDs.

[Sample]

CSCI-wide software design decisions for the XY ProjectCDLMS system software will be a continuous effort.  The Software Project Manager will direct the conduct of design analyses and trade-offs through Software Design Team  meetings involving all concerned.  The Software Design Team will conduct domain analyses, evaluate CSCI-wide design issues, and formulate decisions for new development, reuse of existing components, and hardware/software architectures.

The system-wide design principles for XY Project are:

-	Establish an initial capability for XY Project upon which to build future enhancements

-	Use COTS open system architecture hardware and system software components

-	Maximize reuse of existing software application packages

[End Sample]

### CSCI Architectural Design

Guidance

The developer shall define and record the architectural design of each CSCI (identifying the SUs comprising the CSCI, their interfaces, and a concept of execution among them) and the traceability between the SUs and the CSCI requirements. The result shall include all applicable items in the architectural design and traceability sections of the SDD. Design pertaining to interfaces may be included in SDDs or in IDDs.

Note: SUs may be made up of other SUs and may be organized into as many levels as are needed to represent the CSCI architecture. For example, a CSCI may be divided into three SUs, each of which is divided into additional SUs, and so on.

[Sample]

The Software Preliminary Design phase begins during development of the SSS and SRS.  Preliminary software design  supports modeling the XY Project system. The model is placed under informal Software Design Team control and is used as input to  the SDD.  The processes associated with preliminary software design are:

-	Specify architectural model

-	Develop class categories/classes/methods

-	Map software requirements

-	Conduct software design review

#### Specify Architectural Model Process

An Architecture Working Group (AWG) is formed to address system-wide architectural issues.  The AWG participants are senior systems and software engineers and representatives from each of the technical groups and teams on the XY Project.   The AWG defines an overall architectural model that depicts the logical and physical software design for XY Project.

ENTRY CRITERIA:

-	Formal design methodology

PRINCIPAL:  Architecture Working Group (AWG)

ACTIVITIES:

- Review available documentation on requirements, assumptions, and constraints.

- Formulate and evaluate architectural alternatives.

- Select architectural model.  Define entity-objects, their interactions, data flow, and functional processes.

- Allocate known  requirements to architectural components.

- Review architectural model and requirements allocation.

- Software Project Manager accepts architectural model.

EXIT CRITERIA:

-	Architectural model accepted

-	Requirements allocated  to architectural components

#### Develop Class Categories/Classes/Operations

The Develop Class Categories/Classes/Operations process follows an OOD methodology to identify the top-level class categories, subordinate class categories, and classes for the XY Project software design.  It provides specific definitions of class types, attributes, properties, and operations.

ENTRY CRITERIA:

-	Architectural model accepted

-	Requirements allocated

PRINCIPAL:  Software Design Team

ACTIVITIES:

- Define class generalization hierarchy.

- Define class categories and dependencies.

- Define sub classes.

- Define class attributes.

- Define class operations.

- Update architectural model.

- Review and approve updated architectural model.

EXIT CRITERIA:

-	Class categories/classes defined

-	Architectural model updated

#### Map Software Requirements Process

The Software Design Team maps software requirements from the SSS  to classes.  The mapping process may be repeated several times during the incremental design of the software.

ENTRY CRITERIA:

-	Class categories/classes defined

-	Known software requirements identified

PRINCIPAL:  Software Design Team

ACTIVITIES:

- Review known software requirements and identified class categories and classes.

- Using unique requirement identifiers, map the identified software requirements to classes.

- The Architecture Working Group verifies completeness and consistency of requirements mapping.

EXIT CRITERIA:

-	Software requirements mapped to classes

#### Conduct Software Design Review Process

Software Design Reviews occur at all levels of the software design—from Top-Level through Detailed, and can encompass all or part of any set of software units. The Software Design Team submits a software design package  for review.  Review schedule is coordinated with the Software Development Manager.  Separate reviews may be conducted for overall Top-Level Design, or for localized software units.  The Software Design Team includes the  results of the Software Design review conducted  and the action items identified and tracked to closure in the SDF for the reviewed software.

ENTRY CRITERIA:

-	Software design  ready for review

PRINCIPAL:  Software Development Manager

ACTIVITIES:

- Software Design Team notifies Software Development Manager of readiness for software design review.

- Select software design review team participants, assign roles, and schedule review.

- Distribute software design review package to review participants.

- Conduct software design review.  Software Design Team leader presents the design.  Participants assess compliance with requirements, completeness, efficiency, and adherence to design methodology.  Participants identify and discuss defects.  Recorder documents defects, action items, and recommendations.  Software designer includes record of software design review in SDF.

- Software Design Team corrects any defects in design.  Update design review material as required.  Distribute recorded design review information

- The Software Development Manager obtains the Software Project Manager’s approval of the  software design.

EXIT CRITERIA:

-	Approved software design

### CSCI Detailed Design

Guidance

The developer shall develop and record a description of each software unit. The result shall include all applicable items in the detailed design section of the SDD.  Design pertaining to interfaces may be included in SDDs or in IDDs and design of software units that are databases or that access or manipulate databases may be included in SDDs or in DBDDs.

[Sample]

Detailed software design incrementally defines and describes selected class instances (objects) and their relationships in Interaction Diagrams through a refinement of existing design artifacts.  The architectural model representing each reviewed increment of software design for the XY Project is placed under formal control and is used as input to the SDD.

#### Detailed Design Process

The Software Design Team develops Interaction Diagram elaborating the software design.   If development of Interaction Diagrams identifies deficiencies in class category/class definitions and relationships, the Software Design Team will further refine class definitions and update the developmental architectural model accordingly.

ENTRY CRITERIA:

-	Software Top-Level Design approved

PRINCIPAL:  Software Design Team

ACTIVITIES:

- Construct Interaction Diagrams for class instances (objects).

- Add attributes and operations to each class.

- Allocate software requirements to classes.

- Conduct peer review of class definitions and interaction diagrams. Repeat process several times until detailed design meets peer approval.

EXIT CRITERIA:

-	Interaction diagrams and classes defined and reviewed

[End Sample]

## SOFTWARE IMPLEMENTATION AND UNIT TESTING

Guidance

This paragraph shall be divided into the following subparagraphs to describe the approach to be followed for software implementation and unit testing. The planning in each subparagraph shall cover all contractual clauses regarding the identified topic.

Note: The term "software" includes both computer programs and computer databases. The term "implementation" means converting software design into computer programs and computer databases. If a CSCI is developed in multiple builds, software implementation and unit testing of that CSCI will not be completed until the final build. Software implementation and unit testing in each build should be interpreted to include those units, or parts of units, needed to meet the CSCI requirements to be implemented in that build.

[Sample]

The purpose of Software Implementation and Unit Testing is to implement, and test the detailed design for SUs into new code, or as modifications of existing NDI code following documented programming style guidelines.

The following paragraphs describe Software Implementation and Unit Testing processes.

[End Sample]

### Software Implementation

Guidance

The developer shall develop and record software corresponding to each SU in the CSCI design. This activity shall include, as applicable, coding computer instructions and data definitions, building databases, populating databases and other data files with data values, and other activities needed to implement the design. For deliverable software, the developer shall obtain acquirer approval to use any programming language not specified in the contract.

Note: SUs  in the design may or may not have a one-to-one relationship with the code and data entities (routines, procedures, databases, data files, etc.) that implement them or with the computer files containing those entities.

[Sample]

The Software Development Manager will assign XY Project SUs to individual software engineers forming the Software Production Team.  Software Implementation consists of the following processes:

-	Coding

-	Code Walkthrough

-	SDF Update

Software will be developed using <List of acceptable Languages>.

#### Coding Process

The engineers will analyze the system, software requirements, and design artifacts for their assigned SUs.  They will document the elaborated software design and requirements data into the SDFs and implement the SU using the appropriate language and compilers/interpreters for their development effort.

ENTRY CRITERIA:

-	Compilers/Interpreters available

-	Development lab established

-	Programming style guidelines established

-	Detailed Design under Configuration Control

PRINCIPAL:  Software Production Team

ACTIVITIES:

- Ensure all tools are available to developers in development environment.

- Review requirements documentation and guidelines.

- Maintain working source for assigned task within the Software Library.

- Adhere to software guidelines for code and header comments.

- Compile software.

- Prepare for code walkthrough.

- Document and report design errors/inconsistencies.

- Conduct informal peer code reviews.

- Update metrics information.

- Perform integration testing.

EXIT CRITERIA:

-	Clean compile of SU produced

-	XY Project metrics database revised

#### Code Walkthrough Process

Code walkthroughs will be performed after a clean compile is generated for an SU and will conform to walkthrough procedures.  Informal  reviews will be conducted before presenting the SU to a formal walkthrough proceeding.  Defects identified during the walkthrough will be documented in the SDF and incorporated into the SU.  The SU will then be available for further inspection as required.

ENTRY CRITERIA:

-	SU requirements and design completed in SDF

-	SU coded and compiled error free

ACTIVITIES:

- Prepare code walkthrough package (source code, design documentation).

- Conduct walkthrough.

- Record identified errors.

- Correct identified errors.

EXIT CRITERIA:

-	Results of walkthrough recorded in SDF

-	Corrected SU placed under Configuration Control

#### Software Development File Update

SDFs will be maintained for each SU by the assigned engineer.  The SQA Group  will conduct informal audits on randomly selected SDFs to ensure compliance with the project guidelines.

ENTRY CRITERIA:

-	Requirements identified for SU

-	Detailed Design documented for SU

-	SU assigned to engineer

ACTIVITIES:

-	Update SDF software design and requirements information.

-	Update SDF with compiled software and walkthrough comments

EXIT CRITERIA:

-	Place SDF under Configuration Control

#### Support Tools

The staff will use support tools to aid in developing and modifying XY Project software during coding and unit testing.  Coding and unit test support tools include input/output drivers/simulators/emulators, data recording/extraction/reduction/analysis programs to verify module performance, complexity measurers to provide an early assessment of quality and maintainability, and logic path analyzers to measure completeness of coverage of unit testing.

[End Sample]

### Preparing for Unit Testing

Guidance

The developer shall establish test cases (in terms of inputs, expected results, and evaluation criteria), test procedures, and test data for testing the software corresponding to each SU. The test cases shall cover all aspects of the unit’s detailed design. The developer shall record this information in the appropriate SDFs.

[Sample]

The purpose of unit testing is to identify and correct as many internal logic errors as possible.  Problems not uncovered by unit testing are in general, more difficult to isolate when uncovered at the component or Configuration Item (CI)Configuration Item (CI) level.  Unit testing will be conducted throughout the implementation process, first as part of the initial development process and later as changes to the unit are made.  Unit tests will be repeatable and may be conducted at any point in the implementation process in accordance with the approved unit test plan.  For the purposes of unit testing a unit is an object.  The goal for unit testing by  developers is to perform selected path testing in which every affected branch is navigated in all possible directions at least once and every affected line of code is executed at least once.  Unit test drivers and stubs will be developed as needed and will be placed under configuration control as part of the overall test utility.  All unit test results will be recorded in the SDFs.

#### Unit Test Development

A comprehensive set of repeatable unit tests and test cases will be developed to ensure the correctness of each SU.  The unit test developer is usually the developer of the SU to be tested. Inputs for the development of unit tests include the following:

-	STP

-	SDF for software unit

ENTRY CRITERIA:

-	Software unit design complete.

PRINCIPAL:  Software Production Team

ACTIVITIES:

Activities for unit test development include the following:

- Review the STP to determine the types of unit tests required for the software unit.

- Review all inputs and outputs for the software unit.  Determine the methodology(s) for providing inputs and obtaining outputs. Identify any test drivers necessary to stimulate unit execution, provide inputs, and capture final outputs.  Identify all interfaces to other units and determine if other units are available or if unit stubs must be written.  Consider using stubs to capture intermediate results if other automated tools are not available.

- Identify the various paths that may be taken by the unit (a McCabe complexity analysis tool may be used to determine the unit paths).  Identify data variables and conditions that determine which paths are taken.  Identify parameter limits for all input, output, and control parameters.  Examine and list all error handling facilities of the units and error conditions.

- Identify a set of test cases to conduct the required unit testing (path testing, boundary condition testing, and input validation and syntax testing).  There should be a test case for each path through the unit, to test the upper and lower limits of all parameters, and to test all error conditions (pass and fail).  Write step-by-step procedures for each test case.  Document the unit test and test cases in the SDF.

- Submit the unit test plan for peer review.  Resolve all comments.

EXIT CRITERIA:

Outputs from the development of unit tests include the following:

-	Unit Test Plan documented in SDF

-	Successful peer review of unit test plan

[End Sample]

### Performing Unit Testing

Guidance

The developer shall test the software corresponding to each SU. The testing shall be in accordance with the unit test cases and procedures.

[Sample]

Unit testing  will cover the following areas:

-	Path Testing - Execution of every logic branch and line of code to find logic errors in control structures, dead code, errors at loop boundaries, and errors in loop initializations.  This includes every state and every mode.

-	Boundary Condition Testing - To find errors in input and output parameter tolerances and verify that the program limits are correctly stated and implemented.

ENTRY CRITERIA:

-	Unit  test plan approved and unit software under developmental configuration control

PRINCIPAL:  Software Production Team

ACTIVITIES:

Unit testing activities are as follows:

- Review the unit test plan and retrieve copies of software to be tested and any existing unit test software from the Software Library.

- Develop any unit test drivers and stubs identified in the unit test plan that do not already exist.  Update existing unit test drivers and stubs in response to approved unit and unit test plan changes.

- Perform the test in accordance with the unit test plan.

- Compare test results with expected results.  Document the results on a project unit test report form.  If discrepancies are found, attempt to determine whether the errors are associated with the software, test/test driver, or hardware.

- If problems are found in the software or unit test plan, fix the problem.

- Document all test results in the SDF.  This report should contain all data recorded from test tools, test results, and deviations from test.

- Provide a copy of the SDF’s unit test report to the Software Development Manager for review.  Resolve all comments.

- If the unit did not successfully pass unit test, schedule the unit for rework with the Software Development Manager.

- The Software Development Manager upon successful completion of the unit test, promotes the software unit for integration testing and verifies that all unit tested software is under developmental configuration control.

EXIT CRITERIA:

Output from the unit testing process include the following:

-	Updated SDF

-	Successfully tested unit

METRICS

-	Number of defects detected per SU at Unit Test Time.

[End Sample]

### Revision and Retesting

Guidance

The developer shall make all necessary revisions to the software, perform all necessary retesting, and update the SDFs and other software products as needed, based on the results of unit testing.

[Sample]

The staff  will resolve all anomalies identified in unit testing; make necessary revisions to requirements, design and code, retest, and update SDFs of SUs undergoing coding changes based on unit tests.

[End Sample]

### Analyzing and Recording Unit Test Results

Guidance

The developer shall analyze the results of unit testing and shall record the test and analysis results in appropriate SDFs.

[Sample]

The Software Development Manager will analyze and record results of all unit testing in the project’s metric database.

[End Sample]

## UNIT INTEGRATION AND TESTING

Guidance

This paragraph shall describe the approach to be followed for unit integration and testing.

Note 1: Unit integration and testing means integrating the software corresponding to two or more SUs, testing the resulting software to ensure that it works together as intended, and continuing this process until all software in each CSCI is integrated and tested.  The last stage of this testing is developer-internal CSCI testing. Since units may consist of other units, some unit integration and testing may take place during unit testing. The requirements in this section are not meant to duplicate those activities.

Note 2: If a CSCI is developed in multiple builds, unit integration and testing of that CSCI will not be completed until the final build. Unit integration and testing in each build should be interpreted to mean integrating software developed in the current build with other software developed in that and previous builds, and testing the results.

[Sample]

The Software Test and Evaluation Group  will be integrating SUs and CSCI components for XY Project.

At this level, SUs are incrementally integrated to form continually larger and more complex software builds.  The purpose of this level of testing is to both identify errors and demonstrate interface compatibility.  Integration continues until all software CIs are integrated with the system-level hardware suite into a single functioning software system.

[End Sample]

### Preparing for Unit Integration and Testing

Guidance

The developer shall establish test cases (in terms of inputs, expected results, and evaluation criteria), test procedures, and test data for conducting unit integration and testing. The test cases shall cover all aspects of the CSCI-wide and CSCI architectural design. The developer shall record this information in the appropriate SDFs and may as an option develop an Integration Test Plan.

[Sample]

Before unit integration and testing can begin, an Integration Test Plan must be developed.  The development of the Integration Test Plan is the responsibility of the Software Test and Evaluation Manager.

ENTRY CRITERIA:

-	STP

-	SDP

-	Software Build Schedule

-	Any previous integration test reports

-	SDFs for software units and CIs to be integrated

-	SDFs for the software build

-	Contents of the software build defined

PRINCIPAL:  Integration Test Team

ACTIVITIES:

Activities for the development of the Integration Test Plan are as follows:

- Software Test and Evaluation Group initiates the integration test planning activities.  Schedule and conduct a kick-off meeting with the Integration Test Team to give an overview of the integration test activities.  Review the schedule for completion of the integration test planning activities and the responsibilities of each team member.

- Review the software test plan to determine the types of integration tests to be conducted.  Review the build schedule, the list of software units/components to be included in the build, and the results of any previous integration tests to determine the software and software fixes to be tested.  Determine a set of tests to be developed to test the build.  Review software design information in the SDFs, if necessary, to determine test conditions necessary to execute the desired paths

- For each integration test identified for the build, develop an integration test plan.  The integration test plan should identify the build to be tested, the contents of the build, the requirements to be validated by the test, test tools and drivers to be used, input data, expected output data, and a set of procedures for conducting the test and analyzing the results.  Document the test plan using the project integration test form.

- Submit the integration test plan(s) for peer review.  Resolve all comments.

- Submit integration test plan(s) to the Software Test and Evaluation Manager for review and approval.  Resolve all comments.

- Software Test and Evaluation Manager places a copy of the integration test plan in the associated component/build SDF.

- Software Test and Evaluation Manager places the integration test plan under developmental configuration control.

EXIT CRITERIA:

-	Integration test plan approved and under developmental configuration control.

[End Sample]

### Performing Unit Integration and Testing

Guidance

The developer shall perform unit integration and testing. The testing shall be in accordance with the unit integration test plan and procedures.

[Sample]

The performance of unit integration and testing in accordance with the approved integration test plan(s) is the responsibility of the Software Test and Evaluation Manager, and Integration Test Team.  It includes the development of any test drivers and tools as well as the execution, reporting, and review of test results.

ENTRY CRITERIA:

-	Integration Test Plan

-	SDFs for build

-	Build Directive form

-	Integration Test Report form

-	P/CR form

-	Test drivers and test inspection tools

PRINCIPAL:  Integration Test Team

ACTIVITIES:

Activities for the performance of unit integration and testing are as follows:

- Software Test and Evaluation Manager generates a build request using the project build directive form and assigns the task to the Integration Test Team.  Submit the build directive to the Software Development Manager for review and approval.  Submit the approved build directive to the Software Librarian.

- Upon receipt of the requested build, install it in the integration test area.

- Review the integration test plan.  Develop any test drivers or analysis tools identified in the test plan that do not already exist.  Update any existing test drivers/tools in response to approved software changes/fixes.

- Conduct the test in accordance with the integration test plan procedures.  Record test results as they are observed.

- Perform any required post test analysis or data reduction to determine pass/fail criteria as specified in the integration test plan.

- Compare test results with expected results.  If discrepancies are found, attempt to determine whether errors are associated with the software, test/test driver, or hardware.

- Document all test results using the project integration test report form.  This report should contain all data recorded from test tools, test results, and deviations from the test plan.  Document any problems detected on a P/CR form.

- Software Test and Evaluation Manager reviews the integration test report and any P/CRs for accuracy and thoroughness.  File the test report in the build SDF and submit a copy of the test report and P/CRs to the Software Development Manager for review and analysis.

EXIT CRITERIA:

Exit criteria from the unit integration and testing phase are the following:

-	Integration test report reviewed and approved

-	Updated SDFs.

-	P/CRs submitted for all detected problems

METRICS

-	Number of defects detected during unit integration testing.

[End Sample]

### Revision and Retesting

Guidance

The developer shall make all necessary revisions to the software, perform all necessary retesting, and update the SDFs and other software products as needed, based on the results of unit integration and testing.

[Sample]

The Integration Test Team will make all necessary revisions to the design and code, perform all retesting, and update the appropriate SDFs based on the results of the unit integration and testing phase.

[End Sample]

### Analyzing and Recording Unit Integration and Test Results

Guidance

The developer shall analyze the results of unit integration and testing and shall record the test and analysis results in appropriate SDFs.

[Sample]

The staff will analyze and record the test results of all unit integration and testing in the appropriate build SDF(s).  The Software Project Manager will track any outstanding P/CRs, prioritize them, and submit them for rework and retest as needed.

[End Sample]

## CSCI QUALIFICATION TESTING

Guidance

This paragraph shall describe the approach to be followed for CSCI qualification testing.

Note 1: CSCI qualification testing is performed to demonstrate to the acquirer that CSCI requirements have been met. It covers the CSCI requirements in SRSs and in associated IRS.

Note 2: If a CSCI is developed in multiple builds, its CSCI qualification testing will not be completed until the final build for that CSCI, or possibly until later builds involving items with which the CSCI is required to interface. CSCI qualification testing in each build should be interpreted to mean planning and performing tests of the current build of each CSCI to ensure that the CSCI requirements to be implemented in that build have been met.

[Sample]

The CSCI Test Team will conduct CSCI Qualification Testing on each of the components of the XY Project CSCI.  The purpose of CSCI Qualification Testing is to verify satisfaction of CSCI performance requirements documented in the SRS.

The following paragraphs describe CSCI Qualification Testing processes and assignment of responsibilities. The STP and STDs will provide the detailed plan and design for CSCI Qualification Testing in conformance with these processes.

[End Sample]

### Independence in CSCI Qualification Testing

Guidance

The person(s) responsible for qualification testing of a given CSCI shall not be the persons who performed detailed design or implementation of that CSCI. This does not preclude persons who performed detailed design or implementation of the CSCI from contributing to the process, for example, by contributing test cases that rely on knowledge of the CSCI’s internal implementation.

[Sample]

The Software Test and Evaluation Manager will be responsible for CSCI Qualification testing, reporting directly to the Software Project Manager.  The Software Test and Evaluation Manager will designate a Test Director and assign personnel to the CSCI  Test Team.

[End Sample]

### Testing on the Target Computer System

Guidance

CSCI qualification testing shall include testing on the target computer system or an alternative system approved by the acquirer.

[Sample]

CSCI Qualification testing for XY Project will take place only on the target computer system, interfaced with hardware and software components of the software test environment.  This restriction will assure that testing of timing, capacity, throughput, and responsiveness of XY Project CSCI components with respect to performance requirements can be accurately assessed.

[End Sample]

### Prepare for CSCI Qualification testing

Guidance

The developer shall define and record the test preparations, test cases, and test procedures to be used for CSCI qualification testing and the traceability between the test cases and the CSCI requirements. The result shall include all applicable items in the STD. The developer shall prepare the test data needed to carry out the test cases and provide the acquirer advance notice of the time and location of CSCI qualification testing.

[Sample]

Preparing for CSCI Qualification Testing consists of the following processes:

-	Plan Software Tests

-	Develop Test Cases

-	Develop Test Procedures

-	Prepare Test Environment

#### Plan Software Tests Process

The CSCI Test Team  will plan software tests, identify test resources and schedule, and prepare tests for insertion in the STP.

ENTRY CRITERIA:

-	SRS under baseline control

PRINCIPAL: CSCI Test Team

ACTIVITIES:

- Review software performance requirements documented in the SRS.

- Define test levels for CSCI testing, including general test requirements, test classes (e.g. stress, erroneous input, maximum capacity, and timing).  Define the overall test concept and objectives supported by the defined tests.

- Identify the environment in which CSCI tests will be conducted.  Define plans for implementing and controlling the test environment.

- Estimate the personnel and other resources required to support the test concept and objectives.

- The Software Test and Evaluation Manager  assigns a Test Director and other personnel to prepare, conduct, analyze data, and report the results of CSCI testing.

- Trace software requirements allocated to CSCI testing to defined tests.  Verify completeness of requirement’s traceability.

- Develop a general schedule of defined tests, including time for problem correction and retest.

- Create the CSCI STP, following the instructions of the assigned documentation standard.  Import requirements allocated to tests using the requirements database tool.

- A peer review is conducted  and the SQA Group reviews the draft STP using quality checklists and criteria.  Verify consistency of the STP with baselined requirements and planning documents.  Recommend revisions, as appropriate.

- Revise draft STP to correct discrepancies and incorporate recommended changes.

- CSCI Test Team publishes final STP.  Approve, distribute, and place under baseline control in the Software Library.

EXIT CRITERIA:

-	All SRS performance requirements allocated to CSCI tests

-	STP approved and under configuration control

#### Develop Test Cases Process

The CSCI Test Team  will develop a set of test cases in keeping with the overall test concept and objectives that adequately verify all allocated performance requirements for the CSCI.

ENTRY CRITERIA:

-	STP published and under control

PRINCIPAL: CSCI Test Team

ACTIVITIES:

- Define the test cases for each level, expressing the purpose and conditions associated with each test case and level.

- For each test case, define the inputs (stimuli to the CSCI under test) required to fulfill the test purpose.

- For each test case, define the expected results (outputs from the CSCI under test in response to inputs) required to fulfill the test purpose.

- Define insertion and extraction methods to/from the CSCI under test.  Identify points of data input/output and volumes of data.

- Define evaluation criteria for test results analysis.  Define ranges of values, capacities, and times for test pass/fail.

- Trace SRS performance requirements to specific test cases.  Verify completeness of requirements allocation.  Install traceability in automated requirements database.

- Identify test environment configuration, interface drivers, database loaders, controllers/monitors, and other test tools to support test case purposes.

EXIT CRITERIA:

-	Inputs, expected results, and evaluation criteria defined for test cases

-	CSCI performance requirements allocated to test cases

#### Develop Test Procedures Process

Develop detailed steps for controlling tests, injecting inputs, recording results, and compare actual to expected results.  Document test cases and steps in the STD.

ENTRY CRITERIA:

-	Test cases defined

-	CSCI performance requirements allocated to test cases

-	Draft user and operator manuals or checklists available

PRINCIPAL:  CSCI Test Team

ACTIVITIES:

- Review software user and operator manuals to identify methods of operator input, use of simulator/emulator tools, and software data recording.

- Define detailed test steps for providing inputs for test cases.

- Define measurable detailed test results for test steps.

- Prepare input data files to provide test stimuli.  Prepare operator logs for the CSCI under test, as well as the test environment.

- Define evaluation steps for conducting post-test test analysis and comparing actual and expected test results.

- Create the STD following the instructions of the assigned documentation standard. Import requirements allocated to test steps using the requirements database tool.

- A peer review and a SQA Group  review is performed on the draft STD using quality checklists and criteria.  Verify consistency of the STD with the STP, baselined requirements, and planning documents.  Recommend revisions, as appropriate.

- Revise draft STD to correct discrepancies and incorporate recommended changes.

- The Software Test and Evaluation Manager   approves, distributes, and places the final STD under baseline control in the Software Library.

EXIT CRITERIA:

-	STD approved and under configuration control

-	Test data files compiled

-	Operator logs assembled

#### Prepare Test Environment Process

Sponsor will define, develop, integrate, verify, and place a test environment under control that will support the CSCI test concept and objectives.

ENTRY CRITERIA:

-	Test resources identified in the SDP

-	STP and STD published and under control

PRINCIPAL:  CSCI Test Team

ACTIVITIES:

- Review test evaluation criteria from SRS for performance requirements allocated to the CSCI.

- Define test environment capacities and functions required to verify performance requirements (e.g. interface driver simulation/emulation, test operator entries, control, and data recording).

- Define operational scenarios that exercise the CSCI under test through all performance requirements.

- Evaluate schedule, performance, equipment, facility, and automation constraints affecting the test environment architecture.

- Define the test environment architecture, including COTS and developmental hardware and software, interfaces with test operators, and interfaces with the CSCI under test.

- Develop or select hardware and software components of the test environment (e.g. simulations/emulations, data recording, test control, operator interfaces).

- Integrate COTS and developmental components of the test environment architecture.  Test the integrated test environment using a hierarchical approach.

- The SQA Group and the Software Test and Evaluation Manager  evaluate the integrated test environment, following a documented plan and procedures.  Certify that the test environment fulfills test criteria for all operational scenarios.  Verify that the test environment interfaces correctly with the CSCI under test.

EXIT CRITERIA:

-	Test environment verified as ready for CSCI testing

-	Test environment under control

#### Assure Readiness for Computer Software Configuration Item Qualification Testing

The Software Test and Evaluation Manager will verify that the CSCI is under baseline control; informal testing of the CSCI components have been completed satisfactorily; test materials are completed; and test personnel and other resources are ready for the start of CSCI testing.

#### Conduct Test Readiness Review Process

As a step preliminary to the conduct of CSCI qualification testing, a review of the individual components or activities that makeup the CSCI testing should be conducted.

ENTRY CRITERIA:

-	CSCI under baseline control

-	Informal testing completed

-	P/CRs resulting from informal testing closed

-	STP and STD approved and under configuration control

-	CSCI test materials completed

-	CSCI test environment certified

PRINCIPAL: Software Test and Evaluation Manager

ACTIVITIES:

- Baseline the CSCIs, following review of integration test results.  Issue Baseline Notification.

- Notify TRR participants.

- The  SCM Manager verifies P/TRs resulting from informal testing are closed and corrections tested.

- Verify STP and STDs are complete and under control.

- Verify CSCI test materials (e.g. data files, test environment, and CSCI operator logs) are complete and in conformance with STDs.

- Verify test environment is certified and operational.  Verify that test environment configuration logs are up-to-date.

- Conduct dry run using CSCI test materials and test environment.  Record discrepancies in Test History log.

- Direct correction of  discrepancies in STP, STD, test materials, and test environment configuration, as necessary.

- The Software Project Manager and the Software Test and Evaluation Manager complete TRR.  Authorize start of CSCI Qualification Testing.

EXIT CRITERIA:

-	Discrepancies and action items assigned during TRR closed

[End Sample]

### Dry Run of CSCI Qualification Testing

Guidance

If CSCI qualification testing is to be witnessed by the acquirer, the developer shall conduct a  dry run of the CSCI test cases and procedures to ensure that they are complete and accurate and that the software is ready for witnessed testing. The developer shall record the results of this activity in appropriate SDFs and shall update the CSCI test cases and procedures as appropriate.

### Performing CSCI Qualification Testing

Guidance

The developer shall perform CSCI qualification testing of each CSCI. The testing shall be in accordance with the CSCI test cases and procedures.

[Sample]

The Test Director will execute CSCI tests in the controlled test environment and collect data recorded by operators and automated means during testing.

#### Execute Tests and Collect Data Process

The following set of steps constitute the process to be followed for performing CSCI Qualification Testing.

ENTRY CRITERIA:

-	TRR completed

PRINCIPAL:  CSCI Test Team

ACTIVITIES:

- The Test Director  meets with the test participants prior to scheduled test to brief participants on roles.  Verify readiness of test configuration and materials.  Conduct pre-test inspections of test hardware configurations and interfaces to external systems.

- Load and initialize test environment to meet prescribed test conditions.  Verify readiness of test drivers and recording devices/media.

- Load and initialize CSCI software to meet prescribed test conditions.

- Execute test, following scripted test steps.  Record results on operator logs and automated recording media.

- On completion of test session, debrief assigned test personnel on test observations.  Inspect operator logs.  Label recording media.

- Process recorded test data to reduce and format them in textual and graphic form.

- The Test Director updates Test History log to record pre-test, in-test, and post-test events, problems identified, and resources used.  Archive recording media.  Provide marked-up operator logs and processed recorded data for post-test analysis.

EXIT CRITERIA:

-	Test results logged

-	Recorded test data processed

-	Test History log updated

[End Sample]

### Revision and Retesting

Guidance

The developer shall make necessary revisions to the software, provide the acquirer advance notice of retesting, conduct all necessary retesting, and update the SDFs and other software products as needed, based on the results of CSCI qualification testing.

[Sample]

Revision and re-testing of the CSCI component depends on analysis of test results and correct identification of problems detected during both test conduct and post-test analysis.

[End Sample]

### Analyze and Record CSCI Qualification Test Results

Guidance

The developer shall analyze and record the results of CSCI qualification testing. The results shall include all applicable items in the STR.

[Sample]

Analyzing and recording CSCI Qualification Test Results consists of the following processes:

-	Analyze and Evaluate Results, Revise Tests

-	Report Test Results

#### Analyze and Evaluate Results, Revise Tests Process

The  CSCI Test Team will compare recorded and processed CSCI test results data with expected results to identify, isolate, and assess the probable causes of errors in the CSCI component under test, CSCI hardware, test environment, or test materials. The  CSCI Test Team will revise tests or prepare P/CRs, as required.

ENTRY CRITERIA:

-	Test results logged

-	Recorded test data processed

PRINCIPAL: CSCI Test Team

ACTIVITIES:

- Correlate test operator logs and processed data by time and source to support post-test analysis.

- Run calculations and statistics on processed test data to provide measures associated with evaluation criteria, using automated tools where available.

- Compare actual test results with expected results (including allowable tolerances) documented in STD procedures. Identify any instances of anomalous or unexpected CSCI performance.  Use automated tools to support such analyses, where available.

- Identify and record discrepancies between actual and expected test results.

- Determine sources of discrepancies between actual and expected test results (e.g. test procedure error, operator error, CSCI error, test environment, and hardware).  Update the Test History log with results of post-test analysis.

- Revise test cases, procedures, and materials to correct discrepancies attributable to test design errors.  Provide STD markups for SCCB approval prior to actual changes in test materials.  Correct errors in test environment configuration and hardware in preparation for retest.  Re-brief test operators or clarify test procedures to correct operator errors.

- Prepare P/CRs for errors attributable to CSCI performance.

EXIT CRITERIA:

-	Test discrepancies identified

-	Test History log updated

-	Erroneous tests revised, as required

-	P/CRs prepared, as required

#### Report Test Results Process

The Software Project Manager will evaluate the results of CSCI component tests, determine that test results meet defined objectives, determine that P/CRs are closed and tested, and publish the STR.

ENTRY CRITERIA:

-	Test results analysis completed

PRINCIPAL:  Test Director

ACTIVITIES:

- Review test case purposes and expected results documented in the STD.

- Evaluate actual test results by examining the Test History log, P/CRs, and recorded test data.

- Ensure P/CRs opened during CSCI testing have been tested at informal and CSCI level and closed.  Ensure that adequate regression testing of the updated CSCI version has been conducted and any resulting P/CRs have been tested and closed.

- Calculate test metrics required by the SDP.

- Write test recommendations, promotion to more complex CSCI testing, retest, or completion of CSCI testing, as appropriate to the test level.

- Prepare draft STR, following the instructions of the assigned documentation standard.  Include calculated test metrics data.  Append marked-up data from the STD, processed recorded test data, and Test History log to support test results and recommendations.

- The Software Test and Evaluation Manager and the SQA Group will review the draft STR using quality checklists and criteria.  Verify consistency of the STR with recorded result data.  Recommend revisions, as appropriate.

- Revise draft STR to correct discrepancies and incorporate recommended changes.

- The Software Project Manager will approve, distribute, and place in the Software Library the final STR.

EXIT CRITERIA:

-	CSCI component test objectives demonstrated by results of analysis

-	P/CRs resulting from CSCI component testing closed and tested

-	STR published

[End Sample]

## CSCI/HWCI INTEGRATION AND TESTING

Guidance

This paragraph shall describe the approach to be followed for participating in CSCI/HWCI integration and testing. The planning in each subparagraph shall cover all contractual clauses regarding the identified topic.

Note 1: CSCI/HWCI integration and testing means integrating CSCIs with interfacing HWCIs and CSCIs, testing the resulting groupings to determine whether they work together as intended, and continuing this process until all CSCIs and HWCIs in the system are integrated and tested. The last stage of this testing is developer-internal system testing.

Note 2: If a system or CSCI is developed in multiple builds, CSCI/HWCI integration and testing may not be complete until the final build. CSCI/HWCI integration and testing in each build should be interpreted to mean integrating the current build of each CSCI with the current build of other CSCIs and HWCIs and testing the results to ensure that the system requirements to be implemented in that build have been met.

[Sample]

Upon completion of the testing and integration of all builds and the preliminary integration testing of all CSCI components comprising the XY Project, the software is ready for CSCI/HWCI Hardware Configuration Item (HWCI)/testing.  CSCI/HWCI testing will be conducted in accordance with the STP and the applicable STD after successful completion of a Test Readiness Review.  The objective is to validate that the XY Project Hardware and Software components can individually be interfaced in accordance with the SRS and IRS/IDD requirements and that the components taken as a system are stable enough to proceed with System Qualification Testing.  These tests are formally conducted by a test team composed of personnel from the System Test Organization,  and in conjunction with the software developers.  The IV&V agent will be  present during these tests as an observer.  A STR is prepared to document the results of the test, as delineated in the STP.

[End Sample]

### Preparing for CSCI/HWCI Integration and Testing

Guidance

The developer shall participate in developing and recording test cases (in terms of inputs, expected results, and evaluation criteria),  test procedures, and test data for conducting CSCI/HWCI integration and testing. The test cases shall cover all aspects of the system-wide and system architectural design. The developer shall record software-related information in appropriate SDFs.

[Sample]

Preparation for integration and testing of software and hardware will require the acquisition of the HW and/or HW simulators in configurations to support all planned platforms   Test plans and procedures will need to be developed and implemented. The System Test Organization in preparing for CSCI/HWCI Qualification Testing will perform the following processes:

#### Plan Software Tests Process

The System Test Organization will plan CSCI/HWCI software tests, identify test resources and schedule, and prepare the inputs to the STP.

#### Develop Test Cases Process

The System Test Organization will develop a set of test cases in keeping with the overall test concept and objectives that adequately verify all allocated performance requirements for the CSCI.

#### Develop Test Procedures Process

The System Test Organization will develop detailed steps for controlling tests, injecting inputs, recording results, and comparing actual to expected results.  Once verified, the System Test Organization  will document test cases and steps in the STD.

#### Prepare Test Environment Process

The Project Manager will define, develop, integrate, verify, and place a test environment under control that will support the CSCI test concept and objectives.

#### Assuring Readiness for Hardware Configuration Item/ Computer Software Configuration Item Integration and Testing

The testing will be performed with the equipment at Project Manager’s designated System Test Organization. The System Test Organization will verify that the software and hardware is under baseline control; informal testing of the CSCI component has been completed satisfactorily; informal testing of the hardware has been completed satisfactorily; test materials are completed; test personnel and other resources are ready for the start of CSCI/HWCI testing.

#### Conduct Test Readiness Review

As a step preliminary to the conduct of CSCI/HWCI qualification testing, a review of the individual components or activities which go into the makeup of the testing will be conducted by the Project Manager   in the form of a Test Readiness Review (TRR).

[End Sample]

### Performing CSCI/HWCI Integration and Testing

Guidance

The developer shall participate in CSCI/HWCI integration and testing. The testing shall be in accordance with the CSCI/HWCI integration test cases and procedures.

[Sample]

The System Test Organization will execute CSCI tests in the controlled test environment and collect data recorded by operators and automated means during testing.

[End Sample]

### Revision and Retesting

Guidance

The developer shall make necessary revisions to the software, participate in all necessary retesting, and update the appropriate SDFs and other software products as needed, based on the results of CSCI/HWCI integration and testing.

[Sample]

Revision and re-testing of a CSCI depends on analysis of test results and correct identification of problems detected during both test conduct and post-test analysis.  Therefore, one of the processes described incorporates revision and re-testing.

[End Sample]

### Analyzing and Recording CSCI/HWCI Integration and Test Results

Guidance

The developer shall participate in analyzing the results of CSCI/HWCI integration and testing. Software-related analysis and test results shall be recorded in appropriate SDFs.

[Sample]

The final results of the XY Project CSCI/HWCI integration testing will be documented.  The test report will be distributed for review and approval.  Analyzing and recording CSCI/HWCI Integration Test Results consists of the following processes:

-	Analyze and Evaluate Results, Revise Tests

-	Report Test Results

#### Analyze and Evaluate Results, Revise Tests Process

The System Test Organization will compare recorded and processed CSCI/HWCI integration test results data with expected results to identify, isolate, and assess the probable causes of errors in the CSCIs under test, hardware, test environment, or test materials.  Assigned test personnel will revise tests or prepare P/CRs, as required.

#### Report Test Results Process

The System Test Organization will evaluate the results of CSCI/HWCI integration tests, determine that test results meet defined objectives, determine that P/CRs are closed and tested, and publish the STR.

[End Sample]

## SYSTEM QUALIFICATION TESTING

Guidance

This paragraph shall describe the approach to be followed for participating in system qualification testing. The planning in each subparagraph shall cover all contractual clauses regarding the identified topic.

Note 1: System qualification testing is performed to demonstrate to the acquirer that system requirements have been met. It covers the system requirements in the SSSs and in associated IRSs. This testing contrasts with developer-internal system testing, performed as the final stage of CSCI/HWCI integration and testing.

Note 2: If a system is developed in multiple builds, qualification testing of the completed system will not occur until the final build. System qualification testing in each build should be interpreted to mean planning and performing tests of the current build of the system to ensure that the system requirements to be implemented in that build have been met.

[Sample]

XY Project System Qualification Testing consists of complementary and progressive test phases.  Once CSCI/HWCI is completed by the System Test Organization, System Qualification Testing (SQT)System Qualification Testing (SQT) begins.

A single STP will be generated to address the planning for all levels of software SQT.  A STD will be generated for each CSCI component, documenting the test procedures to be run to verify each requirement in the SRS for that component.  A cross reference matrix will be provided, using the project wide requirements traceability database, to document the test or tests that satisfy each SRS requirement.  A STR will be generated for each CSCI component, documenting the results of each CSCI component test.  The System Test Organization is responsible for generating the appropriate test documentation. The Software Project Manager is responsible for conduct of the tests.  The software developers will be responsible for supplying test procedures for SUs they develop to the System Test Organization for each CSCI component so that they can be incorporated into the STD for system.

The XY Project program will use a series of builds to integrate the various components of the system.  This allows for progress to be measured and demonstrated as more capabilities are added to the baselines.  The testing processes described in this document, up through System Qualification Testing (SQT)System Qualification Testing (SQT), will be used on each of the components as they are approved for delivery and test.  The System Qualification Testing (SQT)System Qualification Testing (SQT)  test will be used to validate the entire systems performance.

The System Qualification Testing (SQT)System Qualification Testing (SQT) is the Project Manager’s approved and witnessed series of tests that demonstrate compliance with the requirements set forth in the XY Project SSS.  The SQT is the acceptance mechanism for the developer’s compliance with the terms of tasking with the Project  Manager.

[End Sample]

### Independence in System Qualification Testing

Guidance

The person(s) responsible for fulfilling the requirements in this section shall not be the persons who performed detailed design or implementation of software in the system. This does not preclude persons who performed detailed design or implementation of software in the system from contributing to the process, for example, by contributing test cases that rely on knowledge of the system’s internal implementation.

[Sample]

The SQT shall be accomplished by the System Test Organization.  This is done to ensure that the product accepted by the government meets all  system requirements.  The Project Manager may approve on a case-by-case basis the use of the developer’s test staff as SQT testers.  However, the conduct of these tests shall remain the responsibility of the System Test Organization.

[End Sample]

### Testing on the Target Computer System

Guidance

The developer’s system qualification testing shall include testing on the target computer system or an alternative system approved by the acquirer.

[Sample]

The target computer system shall be used for all SQT testing.  In the event that commercial equivalents are the only system available, System Engineering shall certify that the commercial equivalent system has the same functional characteristics as the Target Computer System.  If the systems are not equivalent, then the follow-on tests will include a test sample of those procedures that could not be run on the Target Computer System.

[End Sample]

### Preparing for System Qualification Testing

Guidance

The developer shall participate in developing and recording the test preparations, test cases, and test procedures to be used for system qualification testing and the traceability between the test cases and the system requirements. For software systems, the results shall include all applicable items in the STD.  The developer shall participate in preparing the test data needed to carry out the test cases and in providing the acquirer advance notice of the time and location of SQT.

[Sample]

SQT will be conducted at the System Test Organization facilities.  Following SQT the program then proceeds to a series of Demonstration Tests (DTs). Demonstration Tests (DTs) An Operational Evaluation (OPEVAL)Operational Evaluation (OPEVAL) may or may not be conducted based upon the changes to the System Baseline.  Since tests following SQT are performed by external agencies, the processes for these tests have not been discussed.

[End Sample]

### Dry Run of System Qualification Testing

Guidance

If system qualification testing is to be witnessed by the acquirer, the developer shall participate in dry running the system test cases and procedures to ensure that they are complete and accurate and that the system is ready for witnessed testing. The developer shall record the software-related results of this activity in appropriate SDFs and shall participate in updating the system test cases and procedures as appropriate.

[Sample]

The system test procedures will be reviewed and approved prior to conduct of the SQT.  This will allow the developers and testers an early view into problems and issues that might not otherwise be revealed until system testing.

[End Sample]

### Performing System Qualification Testing

Guidance

The developer shall participate in system qualification testing. This participation shall be in accordance with the system test cases and procedures.

[Sample]

The SQT is intended to verify program performance in accordance with the SSS for the XY Project and those requirements specifications referenced from the SRS.  The test will include all functional areas and interfaces to verify the functionality of a totally integrated program.  Program reliability will be evaluated during independent functional and simultaneous operations, and in light and dense tactical environments.  All functions and subsystem interfaces will be independently tested in a systematic manner.  Approved test procedures will be developed to allow for repeatability of tests and to facilitate performance analysis.  System performance will be visually analyzed, augmented by automated data collection, and results will be recorded by test personnel.

SQT components and objectives are as follows:

- Functional Tests - Functional Tests comprise two parts:  Functional Operability Testing (FOT)Functional Operability Testing (FOT) and Functional Stress Testing (FST).Functional Stress Testing (FST).  FOT and FST test the functional requirements and the functional stress requirements of the SRS.  FOT and FST are combined within a single set of procedures.

- Non-tactical Software Tests - In recognition of the object oriented design of XY Project and the direct impact of the production tools on the operation of the program, the resident and non-resident non-tactical tools and modules will be tested explicitly.

- Interface Validation Tests (IVT)Interface Validation Tests (IVT) - IVTs comprise three parts: Interface Message Tests (IMT),Interface Message Tests (IMT), Interface Recovery Tests (IRT)Interface Recovery Tests (IRT) and Interface Stress Tests (IST).Interface Stress Tests (IST).  These three components test all interface messages, software recovery from interface protocol errors, and software response to interface stress, respectively.  All IVTs are run with simulators, and to the degree feasible, will be conducted prior to SQT.

- Regression Tests - Regression tests are run to verify that program changes implemented following the beginning of SQT testing have not introduced program regression.  System tests including a casualty test is included in the Regression Test set.

- Single Unit Tests - Single Unit Tests are performed for each of the XY Project functional areas to validate the program operation individually in a one-on-one link.

- Multiple Unit Tests - Multiple Unit Tests are performed simultaneously for all of the XY Project functional areas to validate the program operation in a multi-unit environment.

- Stress and Endurance Test - The Stress and Endurance Test is designed to satisfy the stress and endurance requirements for critical computer programs.  Three periods of maximum stress are distributed throughout a 25 hour period.  The program must operate continuously for 25 hours without resulting in a Priority 1 or 2 TR to pass this test.

- P/CR Correction/Closure Tests - These test are executed to verify fixes to problems and to concur with the decision to close.

Specific SQT requirements and processes will be specified in the STP.

[End Sample]

### Revision and Retesting

Guidance

The developer shall make necessary revisions to the software, provide the acquirer advance notice of retesting, participate in all necessary retesting, and update the SDFs and other software products as needed, based on the results of system qualification testing.

[Sample]

The Regression Test (RT),Regression Test (RT) a set of high level tests, will perform a representative sampling of critical XY Project functions.  It will run against a newly delivered operational program during SQT to examine the possibility of regression between the new and previous program versions.  The RT is intended to serve as "system checkout" and should retain a measure of simplicity to ensure that results may be compared from one run to the next.  Requirements for this test will be derived from mission-critical functions and casualty requirements identified in the SSS.  Specific mission-critical functions are chosen which ensure that failure among them does compromise the overall effectiveness of the XY Project.  Testing will be done in a laboratory environment.

[End Sample]

### Analyzing and Recording System Qualification Test Results

Guidance

The developer shall participate in analyzing and recording the results of system qualification testing. For software systems, the result shall include all applicable items in the STR.

[Sample]

Test procedures shall be prepared for each event to be tested in SQT and shall contain clear identification to link it to its particular level of test, as well as to define test objectives. These test procedures shall contain the expected results, a pass/fail notation, and a summary, if applicable.  Evaluations of test data shall provide the basis for a pass/fail determination leading to eventual acceptance or non-acceptance of the program.  Problems in either software or design documentation or user manuals shall be documented as a Problem/Change Report (P/CR).Software Trouble Report (STR).

A P/CR is a report describing an existing problem in a computer program or its support documentation.  Some P/CRs may, in fact, report a design enhancement rather than a design problem, in which case that PR will eventually be closed-out by submission of an ECP.  P/CR priorities are defined below:

a.	High:

1.	Priority 1 - an error which prevents the accomplished of an operational or mission-essential function

2.	Priority 2 - an error which adversely affects the accomplishment of an operational or mission-essential function so as to degrade performance for which no alternative work-around solution exists

b.	Medium:

1.	Priority 3 - an error which adversely affects the accomplishment of an operational or mission-essential function so as to degrade performance and for which there is a reasonable alternative work-around solution.

c.	Low:

1.	Priority 4 - an error which is an operator inconvenience or annoyance, but which does not affect a required operational or mission-essential function

2.	Priority 5 - all other errors P/CR reports fall into one of the following categories:

(a)	Program Trouble (P) - the program does not operate according to reference documentation and the reference documentation is correct; or, the program has a logic error with no directly observable operational symptom, yet has the potential for creating problems.

(b)	Documentation Trouble (D) - the program operates as designed; however, supporting documentation is either incorrect or inadequate.

P/CRs consists of a database of trouble reports with the following kinds of data:  P/CR name, P/CR number, P/CR description, a category specification, a severity specification, and a process state status code.  In addition, P/CR database incorporates a routing system to direct the handling of each P/CR from station to station such as entry, analysis, approval, design, code, test, acceptance, and closure.  The P/CR database program retains comments generated by each station as it advances through the route.  The P/CR database program generates a variety of reports by selected category in specified order.

[End Sample]

## PREPARING FOR SOFTWARE USE

Guidance

This paragraph shall describe the approach to be followed when preparing for software use. The planning in each subparagraph shall cover all contractual clauses regarding the identified topic.

Note: If software is developed in multiple builds, the developer’s planning should identify what software, if any, is to be fielded to users in each build and the extent of fielding (for example, full fielding or fielding to selected evaluators only). Preparing for software use in each build should be interpreted to include those activities necessary to carry out the fielding plans for that build.

[Sample]

The Delivery Team  is responsible for correctly packaging the software according to the XY Project procedures.

[End Sample]

### Preparing the Executable Software

Guidance

The developer shall prepare the executable software for each user site, including any batch files, command files, data files, or other software files needed to install and operate the software on its target computer(s). The result shall include all applicable items in the executable software section of the SPS.

Note: To order only the executable software (delaying delivery of source files and associated support information to a later build), the acquirer can use the SPS, tailoring out all but the executable software.

[Sample]

The executable software will be prepared for each user site, including any batch files, command files, data files, or other software files needed to install and operate the software on its target computer(s).  The result is included in the executable deliverable portion  of the Program Package (PP) as documented in a Software Product Specification (SPS).

[End Sample]

### Preparing Version Descriptions for User Sites

Guidance

The developer shall identify and record the exact version of software prepared for each user site. The information shall include all applicable items in the SVD.

[Sample]

The Software Version  Description (SVD) identifies and describes a version of a CSCI component or interim change (i.e., changes which occur between CSCI versions) to the previously released version.  The SVD records data pertinent to the status and usage of a CSCI version or interim change.  It is used to release CSCI versions or interim changes to the customer and will be included in the Program Package (PP) along with the SPS.

[End Sample]

### Preparing User Manuals

Guidance

The developer shall prepare user manuals in accordance with the following requirements.

Note: Few, if any, systems will need all of the manuals in this section. The intent is for the acquirer, with input from the developer, to determine which manuals are appropriate for a given system and to require the development of only those manuals. All DIDs permit substitution of commercial or other manuals that contain the required information. The manuals in this section are normally developed in parallel with software development, ready for use in CSCI testing.

[Sample]

User Manuals will be prepared by the Software Development Group  and validated by the Software Test and Evaluation Group.   The Software Librarian  will baseline the User Manuals, and provide copies  as part of the deliverable Program Package (PP)

[End Sample]

#### Software User Manuals

Guidance

The developer shall identify and record information needed by hands-on users of the software (persons who will both operate the software and make use of its results). The information shall include all applicable items in the Software Users Manual (SUM).

##### Software Input/Output Manuals

Guidance

The developer shall identify and record information needed by persons who will submit inputs to, and receive outputs from, the software, relying on others to operate the software in a computer center or other centralized or networked software installation. The information shall include all applicable items in the Software Input/Output User Manual (SIOM).

##### Software Center Operator Manuals

Guidance

The developer shall identify and record information needed by persons who will operate the software in a computer center or other centralized or networked software installation, so that it can be used by others. The information shall include all applicable items in the Software Center Operator Manual (SCOM).

##### Computer Operation Manuals

Guidance

The developer shall identify and record information needed to operate the computers on which the software will run. The information shall include all applicable items in the Computer Operation Manual (COM).

### Installation at User Sites

Guidance

The developer shall:

- Install and check out the executable software at the user sites specified in the contract.

b. Provide training to users as specified in the contract.

c. Provide other assistance to user sites as specified in the contract.

[Sample]

Installation and integration schedules must be developed and site surveys completed prior to development of the individual Program Packages (PP).  The installation can begin at the completion of system development.  All hardware and software components must be assembled and tested in a lab environment prior to being shipped to the user site.

The XY Project software and hardware systems will then be shipped to the user site and installed and checked out by the designated Delivery Team.  Each Delivery Team will identify needed training and prepare training materials. Training should be provided to users at the time of installation.  Other assistance, such as user consultation, must be readily available after installation of each revision.

[End Sample]

## PREPARING FOR SOFTWARE TRANSITION

Guidance

This paragraph shall describe the approach to be followed for preparing for software transition. The planning in each subparagraph shall cover all contractual clauses regarding the identified topic.

Note: If software is developed in multiple builds, the developer’s planning should identify what software, if any, is to be transitioned to the support agency in each build.  Preparing for software transition in each build should be interpreted to include those activities necessary to carry out the transition plans for that build.

### Preparing the Executable Software

Guidance

The developer shall prepare the executable software to be transitioned to the support site, including any batch files, command files, data files, or other software files needed to install and operate the software on its target computer(s). The result shall include all applicable items in the executable software section of the SPS.

### Preparing Source Files

Guidance

The developer shall prepare the source files to be transitioned to the support site, including any batch files, command files, data files, or other files needed to regenerate the executable software. The result shall include all applicable items in the source file section of the SPS.

### Preparing Version Descriptions for the Support Site

Guidance

The developer shall identify and record the exact version of software prepared for the support site. The information shall include all applicable items in the SVD.

### Preparing the “As Built” CSCI Design and Other Software Support Information

Guidance

The developer shall update the design description of each CSCI to match the “as built” software and shall define and record: the methods to be used to verify copies of the software, the measured computer hardware resource utilization for the CSCI, other information needed to support the software, and traceability between the CSCI’s source files and SUs and between the computer hardware resource utilization measurements and the CSCI requirements concerning them. The result shall include all applicable items in the qualification, software support, and traceability sections of the SPS.

Note: In hardware development, the final product is an approved design from which hardware items can be manufactured. This design is presented in the product specification. In software development, by contrast, the final product is the software, not its design, and “manufacturing” consists of electronically duplicating the software, not recreating it from the design. The “as built” design is included in the software product specification not as the product but as information that may help the support agency understand the software in order to modify,  enhance, and otherwise support it.

### Updating the System Design Description

Guidance

The developer shall participate in updating the system design description to match the “as built” system. The result shall include all applicable items in the System/Subsystem Design Description (SSDD).

### Preparing Support Manuals

Guidance

The developer shall prepare support manuals in accordance with the following requirements.

Note: Not all systems will need the manuals in this section. The intent is for the acquirer, with input from the developer, to determine which manuals are appropriate for a given system and to require the development of only those manuals. All DIDs permit substitution of commercial or other manuals that contain the required information. The manuals in this section supplement the SSDD and the SPSs, which serve as the primary sources of information for software support. The user manuals cited in 5.12.3 are also useful to support personnel.

#### Computer Programming Manuals

Guidance

The developer shall identify and record information needed to program the computers on which the software was developed or on which it will run.  The information shall include all applicable items in the Computer Programming Manual (CPM).

#### Firmware Support Manuals

Guidance

The developer shall identify and record information needed to program and reprogram any firmware devices in which the software will be installed.  The information shall include all applicable items in the Firmware Support Manual (FSM).

### Transition to the Designated Support Site

Guidance

The developer shall:

- Install and check out the deliverable software in the support environment designated in the contract.

- Demonstrate to the acquirer that the deliverable software can be regenerated (compiled/linked/loaded into an executable product) and maintained using commercially available, acquirer-owned, or contractually deliverable software and hardware designated in the contract or approved by the acquirer.

- Provide training to the support agency as specified in the contract.

- Provide other assistance to the support agency as specified in the contract.

## SOFTWARE CONFIGURATION MANAGEMENT

Guidance

This paragraph shall describe the approach to be followed for software configuration management.  The planning in each subparagraph shall cover all contractual clauses regarding the identified topic.

Note: If a system or CSCI is developed in multiple builds, the software products of each build may be refinements of, or additions to, software products of previous builds. Software configuration management in each build should be understood to take place in the context of the software products and controls in place at the start of the build.

Also refer to the SSC San Diego Software Configuration Management (SCM) Process and the Generic Software Configuration Management Plan (SCMP) Template.  Available on the SEPO home page.

[Sample]

The Software Project Manager will implement SCM processes by designating a SCM Manager and establishing a Local Software CCB  (LCCB) to exercise control of functional, allocated, and product baselines for XY Project deliverables and intermediate products.

Software Configuration Management  will be performed under the direction of the SCM Manager  according the processes and procedures defined in the XY Project  Software Configuration Management Plan (SCMP).

[End Sample]

### Configuration Identification

Guidance

The developer shall participate in selecting CSCIs, as performed under system architectural design in 5.4.2, shall identify the entities to be placed under configuration control, and shall assign a project-unique identifier to each CSCI and each additional entity to be placed under configuration control. These entities shall include the software products to be developed or used under the contract and the elements of the software development environment. The identification scheme shall be at the level at which entities will actually be controlled, for example, computer files, electronic media, documents, software units, configuration items. The identification scheme shall include the version/revision/release status of each entity.

### Configuration Control

Guidance

The developer shall establish and implement procedures designating the levels of control each identified entity must pass through (for example, author control, project-level control, acquirer control); the persons or groups with authority to authorize changes and to make changes at each level (for example, the programmer/analyst, the software lead, the project manager, the acquirer); and the steps to be followed to request authorization for changes, process change requests, track changes, distribute changes, and maintain past versions. Changes that affect an entity already under acquirer control shall be proposed to the acquirer in accordance with contractually established forms and procedures, if any.

Note: A number of requirements in this standard refer to “project-level or higher configuration control.” If “project-level” is not a level of control selected for the project, the software development plan should state how these requirements map to the selected levels.

### Configuration Status Accounting

Guidance

The developer shall prepare and maintain records of the configuration status of all entities that have been placed under project-level or higher configuration control. These records shall be maintained for the life of the contract. They shall include, as applicable, the current version/revision/release of each entity, a record of changes to the entity since being placed under project-level or higher configuration control, and the status of problem/change reports affecting the entity.

### Configuration Audits

Guidance

The developer shall support acquirer-conducted configuration audits as specified in the contract.

Note: These configuration audits may be called Functional Configuration Audits and Physical Configuration Audits.

### Packaging, Storage, Handling, and Delivery

Guidance

The developer shall establish and implement procedures for the packaging, storage, handling, and delivery of deliverable software products.  The developer shall maintain master copies of delivered software products for the duration of the contract.

## SOFTWARE PRODUCT EVALUATION

Guidance

This paragraph shall describe the approach to be followed for software product evaluation. The planning in each subparagraph shall cover all contractual clauses regarding the identified topic.

Note: If a system or CSCI is developed in multiple builds, the software products of each build should be evaluated in the context of the objectives established for that build. A software product that meets those objectives can be considered satisfactory even though it is missing information designated for development in later builds.

[Sample]

The processes defined in the Software Quality Assurance Plan (SQAP) address software product evaluation.

[End Sample]

### In-process and Final Software Product Evaluations

Guidance

The developer shall perform in-process evaluations of the software products generated in carrying out the requirements stated in MIL-STD-498.  In addition, the developer shall perform a final evaluation of each deliverable software product before its delivery.

### Software Product Evaluation Records

Guidance

The developer shall prepare and maintain records of each software product evaluation. These records shall be maintained for the life of the contract. Problems in software products under project-level or higher configuration control shall be handled as described in 5.17 (Corrective action).

### Independence in Software Product Evaluation

Guidance

The persons responsible for evaluating a software product shall not be the persons who developed the product. This does not preclude the persons who developed the software product from taking part in the evaluation (for example, as participants in a walk-through of the product).

## SOFTWARE QUALITY ASSURANCE

Guidance

This paragraph describe the approach to be followed for software quality assurance. The planning in each subparagraph shall cover all contractual clauses regarding the identified topic.

Note: If a system or CSCI is developed in multiple builds, the activities and software products of each build should be evaluated in the context of the objectives established for that build.  An activity or software product that meets those objectives can be considered satisfactory even though it is missing aspects designated for later builds. Planning for software quality assurance is included in software development planning (see 5.1.1).

Also refer to the SSC San Diego Software Quality Assurance (SQA) Process and the Software Quality Assurance Plan (SQAP) Template. Available on the SEPO home page.

[Sample]

The following paragraphs describe processes to initiate and manage SQA functions within the XY Project.  The purpose of SQA is to provide management with appropriate visibility into the processes being used by the software project and of products being built.  The Software Quality Assurance Plan (SQAP)Software Quality Assurance Plan (SQAP) is the guiding document for the conduct of SQA within  the XY Project.

[End Sample]

### Software Quality Assurance Evaluations

Guidance

The developer shall conduct ongoing evaluations of software development activities and the resulting software products to:

- Assure that each activity required by the contract or described in the software development plan is being performed in accordance with the contract and with the software development plan.

b. Assure that each software product required by this standard or by other contract provisions exists and has undergone software product evaluations, testing, and corrective action as required by this standard and by other contract provisions.

### Software Quality Assurance Records

Guidance

The developer shall prepare and maintain records of each software quality assurance activity. These records shall be maintained for the life of the contract. Problems in software products under project-level or higher configuration control and problems in activities required by the contract or described in the software development plan shall be handled as described in 5.17 (Corrective action).

### Independence in Software Quality Assurance

Guidance

The persons responsible for conducting software quality assurance evaluations shall not be the persons who developed the software product, performed the activity, or are responsible for the software product or activity. This does not preclude such persons from taking part in these evaluations. The persons responsible for assuring compliance with the contract shall have the resources, responsibility, authority, and organizational freedom to permit objective software quality assurance evaluations and to initiate and verify corrective actions.

## CORRECTIVE ACTION

Guidance

This paragraph shall describe the approach to be followed for corrective action. The planning in each subparagraph shall cover all contractual clauses regarding the identified topic.

[Sample]

The  XY Project will use the processes for  databasing, tracking, and directing correction of  P/CRs as defined the SCMP.

[End Sample]

### Problem/Change Reports

Guidance

The developer shall prepare a problem/change report to describe each problem detected in software products under project-level or higher configuration control and each problem in the processes described in the SDP.  Problem/change reports may include the following items: project name, originator, problem number, problem name, software element or document affected, origination date, category and priority, description, analyst assigned to the problem, date assigned, date completed, analysis time, recommended solution, impacts, problem status, approval of solution, follow-up actions, corrector, correction date, version where corrected, correction date, and  description of solution implemented.   These reports shall serve as input to the corrective action system.

[Sample]

Problem/Change Reports

The XY Project  corrective action system will process and track all P/CRs to closure, identify quality and performance trends, verify proper processing, and assure implementation and test of approved actions.  The SCM Group  will follow the SCMP to establish and maintain a database of all P/CRs, reflecting SCCB actions, current status, and disposition.  The XY Project managers and technical personnel will access the database to monitor and evaluate all P/CRs, verify the completeness and sufficiency of evaluation and testing of corrective actions, and initiate ECPs, as necessary.

[End Sample]

### Corrective Action System

Guidance

The developer shall implement a corrective action system for handling each problem detected in software products under project-level or higher configuration control and each problem in activities required by the contract or described in the software development plan. The system shall meet the following requirements:

- Inputs to the system shall consist of problem/change reports.

- The system shall be closed-loop, ensuring that all detected problems are promptly reported and entered into the system, action is initiated on them, resolution is achieved, status is tracked, and records of the problems are maintained for the life of the contract.

- Each problem shall be classified by category and priority, using the categories and priorities listed documented in the SCMP,  or approved alternatives.

- Analysis shall be performed to detect trends in the problems reported.

- Corrective actions shall be evaluated to determine whether problems have been resolved, adverse trends have been reversed, and changes have been correctly implemented without introducing additional problems.

[Sample]

The corrective action authority for baselined products will be the XY Project  SCCB.  The corrective action authority for software products under development or modification will be an LCCB.  For corrective action to NDI software CSCI components, the Software Project Manager will interact with the SCCB to resolve corrective actions.  For COTS software elements, the Software Project Manager  will interact with licensed software maintainers to resolve corrective actions and implement version changes.

[End Sample]

## Joint Technical and Management Reviews

Guidance

This paragraph shall describe the approach to be followed for joint technical and management reviews. The planning in each subparagraph shall cover all contractual clauses regarding the identified topic.

Note: If a system or CSCI is developed in multiple builds, the types of joint reviews held and the criteria applied will depend on the objectives of each build. Software products that meet those objectives can be considered satisfactory even though they are missing information designated for development in later builds.

[Sample]

The purpose of technical and management reviews is to provide management with tracking and oversight of the progress of software development undertaken by the XY Project  and fulfillment of requirements.  Timely technical and management reviews at the appropriate level of detail facilitate information reporting and interchange that tracks progress against plans, identify and resolve action items, and verify appropriate expenditure of assigned resources.

[End Sample]

### Joint Technical Reviews

Guidance

The developer shall plan and participate in joint technical reviews at locations and dates proposed by the developer and approved by the acquirer. These reviews shall be attended by persons with technical knowledge of the software products to be reviewed.  The reviews shall focus on in-process and final software products, rather than materials generated especially for the review. The reviews shall have the following objectives:

- Review evolving software products, using as criteria the software product evaluation criteria in Appendix D of MIL-STD-498; review and demonstrate proposed technical solutions; provide insight and obtain feedback on the technical effort; and surface and resolve technical issues.

- Review project status; surface near- and long-term risks regarding technical, cost, and schedule issues.

- Arrive at agreed-upon mitigation strategies for identified risks, within the authority of those present.

- Identify risks and issues to be raised at joint management reviews.

- Ensure ongoing communication between acquirer and developer technical personnel.

The SSC San Diego Formal Inspection Process is an example of a type of Joint Technical Review addressed in paragraph (a) above.

### Joint Management Reviews

Guidance

The developer shall plan and participate in joint management reviews at locations and dates proposed by the developer and approved by the acquirer. These reviews shall be attended by persons with authority to make cost and schedule decisions.  Examples of such reviews are identified in Appendix E of MIL-STD-498.

- Keep management informed about project status, directions being taken, technical agreements reached, and overall status of evolving software products.

- Resolve issues that could not be resolved at joint technical reviews.

- Arrive at agreed-upon mitigation strategies for near- and long-term risks that could not be resolved at joint technical reviews.

- Identify and resolve management-level issues and risks not raised at joint technical reviews.

- Obtain commitments and acquirer approvals needed for timely accomplishment of the project.

Given below is a set of candidate joint management reviews that might be held during a software development project. There is no intent to require these reviews or to preclude alternatives or combinations of these reviews.

1. Software plan reviews. These reviews are held to resolve open issues regarding one or more of the following:

a.  Software Development Plan (SDP)

b.  Software Test Plan (STP)

c.  Software Installation Plan (SIP)

d.  Software Transition Plan (STrP)

2. Operational concept reviews. These reviews are held to resolve open issues regarding the operational concept for a software system.

3. System/subsystem requirements reviews. These reviews are held to resolve open issues regarding the specified requirements for a software system or subsystem.

4. System/subsystem design reviews. These reviews are held to resolve open issues regarding one or more of the following:

a.  The system- or subsystem-wide design decisions

b.  The architectural design of a software system or subsystem

5. Software requirements reviews. These reviews are held to resolve open issues regarding the specified requirements for a CSCI.

6. Software design reviews. These reviews are held to resolve open issues regarding one or more of the following:

a.  The CSCI-wide design decisions

b. The architectural design of a CSCI

c.  The detailed design of a CSCI or portion thereof (such as a database)

7. Test readiness reviews. These reviews are held to resolve open issues regarding one or more of the following:

a.  The status of the software test environment

b.  The test cases and test procedures to be used for CSCI qualification testing or system qualification      testing

c.  The status of the software to be tested

8. Test results reviews. These reviews are held to resolve open issues regarding the results of CSCI qualification testing or system qualification testing.

9. Software usability reviews. These reviews are held to resolve open issues regarding one or more of the following:

a.  The readiness of the software for installation at user sites

b.  The user and operator manuals

c.  The software version descriptions

d.  The status of installation preparations and activities

10. Software supportability reviews. These reviews are held to resolve open issues regarding one or more of the following:

a.  The readiness of the software for transition to the support agency

b.  The software product specifications

c.  The software support manuals

d.  The software version descriptions

e.  The status of transition preparations and activities, including transition of the software development environment, if applicable

11. Critical requirement reviews. These reviews are held to resolve open issues regarding the handling of critical requirements, such as those for safety, security, and privacy.

Also refer to the SSC San Diego “Keys to a Successful Meeting/Review” brief and the Software Management for Executives Guidebook.  Available on the SEPO home page.

## OTHER SOFTWARE DEVELOPMENT ACTIVITIES

Guidance

This paragraph shall describe the approach to be followed for other software development activities.  The planning in each subparagraph shall cover all contractual clauses regarding the identified topic.

[Sample]

These paragraphs describe the technical and management approach to coordinating and providing oversight of software development activities undertaken by the XY Project.  Timely technical and management oversight at the appropriate level is necessary to:

-	Track progress against plans

-	Have mechanisms in place to identify and resolve problems

-	Identify and verify appropriate expenditure of assigned resources

-	Depict activities and relationships associated with planning and conducting integration

-	Consider other related development actions and schedules that could impact XY Project

These paragraphs address those actions to be taken to maintain a broad management picture of XY Project software development.

[End Sample]

### Risk Management

Guidance

The developer shall perform risk management throughout the software development process. The developer shall identify, analyze, and prioritize the areas of the software development project that involve potential technical, cost, or schedule risks; develop strategies for managing those risks; record the risks and strategies in the software development plan; and implement the strategies in accordance with the plan.

Also refer to the SSC San Diego Risk Management Process available on the SEPO home page.

[Sample]

Risk analysis and risk management deal with concerns of project personnel regarding the capability of the designed system to achieve program objectives of technical performance, schedule and cost.  Risk analysis is an iterative process.  It attempts to identify what could go wrong, plan courses of action to mitigate the occurrence, and plan contingencies in the event problems arise.  Risk analysis identifies potential problem areas, quantifies risks associated with these problems, assesses the effect of these risks, and generates alternative actions/mitigations to reduce risks and recover from their occurrence.

The major areas of risk for the software development will be managed following the process identified in the Risk Management Plan.

[End Sample]

### Software Management Indicators

Guidance

The developer shall use software management indicators to aid in managing the software development process and communicating its status to the acquirer. The developer shall identify and define a set of software management indicators, including the data to be collected, the methods to be used to interpret and apply the data, and the planned reporting mechanism. The developer shall record this information in the software development plan and shall collect, interpret, apply, and report on those indicators as described in the plan.  Given below is a set of candidate management indicators that might be used on a software development project. There is no intent to impose these indicators or to preclude others.

a.  Requirements volatility: total number of requirements and requirement changes over time.

b.  Software size: planned and actual number of units, lines of code, and/or other size measurement over time.

c.  Software staffing: planned and actual staffing levels over time.

d.  Software complexity: complexity of each SU.

e.  Software progress: planned and actual number of SUs designed, implemented, unit tested, and integrated over time.

f.  P/CR status: total number, number closed, number opened in the current reporting period, age, priority.

g.  Build release content: planned and actual number of SUs released in each build.

h.  Computer hardware resource utilization: planned and actual use of computer hardware resources (such as processor capacity, memory capacity, input/output device capacity, auxiliary storage device capacity, and communications/network equipment capacity) over time.

i.  Milestone performance: planned and actual dates of key project milestones.

j.  Scrap/rework: amount of resources expended to replace or revise software products after they are placed under project-level or higher configuration control.

k.  Effect of reuse: a breakout of each of the indicators above for reused versus new software products.

Also refer to the Practical Software Measurement (PSM) Guide available on the SEPO home page.

[Sample]

The XY Project  management team will use software metrics for measurement of productivity and quality.  Within the context of software project management, the concern is primarily with productivity and quality metrics (measures of software development unit completion as a function of effort applied and measures of the quality of the output that is produced.)  The Software Project Manager  will require weekly input from the software development participants for this measurement process.  These metrics will in turn be used to calculate cost and schedule variance data.

Metrics collected for  the object oriented OO development will be used to monitor the overall effort and will be collected for each unit.  A unit is herein defined as a unique class, method, or code that has been extracted in whole or part from existing systems.  The following set of metrics will be collected and provided to the Software Manager.

-	Percent each Unit Designed

-	Percent each Unit Implemented/Unit Tested

-	Total Unit Count Code Review completed

-	Total Unit Count completing CSCI Testing

-	Total Unit Count completing Integration Testing

The following set of metrics will be used as planning data for percent calculations and monitoring the developmental progress and volatility:

a.   Projected Unit Count:  derived from requirements and on-going analysis.  This is a metric to be applied throughout the development cycle.

b.   Unit Complexity Weighting:  SUs will be weighted by Easy, Moderate, or Complex to help normalize the calculated percent complete metrics.

[End Sample]

### Security and Privacy

Guidance

The developer shall meet the security and privacy requirements specified in the contract. These requirements may affect the software development effort, the resulting software products, or both.

[Sample]

The XY Project software development is anticipated to contain a limited amount of classified data.  Determination of classification will be in accordance with OPNAVINST S5513.3B, Security Classification Guide.  Development of classified software will occur only in properly cleared spaces utilizing Automated Information Systems (AIS)Automated Information Systems (AIS) approved computers.  Transfer of classified programs between facilities shall utilize approved methods.  The highest security level that should be encountered during software development is SECRET.  Each software engineer or other software support person who requires access to classified material will be cleared to the appropriate level and supplied with an approved container in which classified material can be stored when not in use.

[End Sample]

### Subcontractor Management

Guidance

If subcontractors are used, the developer shall include in subcontracts all contractual requirements necessary to ensure that software products are developed in accordance with prime contract requirements.

Also refer to the SSC San Diego Contractor Acquisition and Monitoring (CAPM) Process. Available on the SEPO home page.

[Sample]

The Software Project Manager  will use the SEPO developed CAPM Process for Software Contracts as a guide for contractor management.  The Software Project Manager will augment the CAPM by initiating additional management actions described below.

Contractor personnel will participate in all development team activities including weekly status meetings, and informal and/or formal reviews as directed by Software Project Manager.   Contractors will supply weekly metrics and monthly status reports on progress against their statement of work as called for in their individual CDRLs.  (Contract data requirements list)Contract Data Requirements List (CDRL).

When deemed necessary, the Software Project Manager will establish working groups made up of government and contractor personnel to address major project areas such as architecture, integration, and display.

The Software Project Manager will also establish an overall XY Project software development, integration, and testing schedule.  Included in this schedule will be all major project milestones which will enable a contractor to plan for delivery of their individual sections.

In order to manage and track XY Project status/progress, the Software Project Manager will direct the use of the software management tool, Microsoft  Project.

[End Sample]

### Interface With Software Independent Verification and Validation (IV&V) Agents

Guidance

The developer shall interface with the software Independent Verification and Validation (IV&V) agent(s) as specified in a tasking statement.

[Sample]

Coordination will be provided by having the IV&V Group participate/monitor activities in each phase of the development process including attending both formal and informal program reviews.  In addition, the IV&V Group will be provided on-line access to source code, test scripts and documentation, and will participate in the SCCB.

During all phases of software development, the IV&V Group will be able to initiate change requests to the evolving baseline or to add their review comments into the active action items to be resolved as a part of each end-of-phase review.  These comments will be treated like any comment or change request initiated by a member of the project organization.  Review comments are expected to be supplied in written form, or electronically in Microsoft Word, for subsequent tracking by the Software Project Manager in the same manner review actions items are handled.  All comments will be adjudicated and responses provided back to the IV&V Manager describing the intended action to be taken.  Change requests to change something in the developmental baseline, after the phase has been completed, will be entered into the configuration control system as described in SCMP and disposed of like any other change request.  The IV&V Group will be able to monitor the status of change requests they submitted directly from the SCM system.

[End Sample]

### Coordination With Associate Developers

Guidance

The developer shall coordinate with associate developers, working groups, and interface groups as specified in the contract.

[Sample]

The Software Project Manager’s and key staff members will meet weekly to clarify issues, obtain project status on deliverables, and elicit program comments.   Updates will be provided and technical issues that affect the overall development effort will be discussed.  In addition, the Software Project Manager will form sub-groups or committees to resolve complex technical and administrative issues.

In order to provide a documentation trail, E-mail will be used as the primary means of distributing data amongst participants.

[End Sample]

### Improvement of Project Processes

Guidance

The developer shall periodically assess the processes used on the project to determine their suitability and effectiveness. Based on these assessments, the developer shall identify any necessary and beneficial improvements to the process, shall identify these improvements to the acquirer in the form of proposed updates to the software development plan and, if approved, shall implement the improvements on the project.

Also refer to the SSC San Diego Software Process Improvement (SPI) Process and the Software Process Improvement Plan (SPIP) Template. Available on the SEPO home page.

[Sample]

As the XY Project program matures, the SDP should undergo revision reflecting improvements to the processes.  Quality and process improvement comes by analyzing and measuring the process in a structured, controlled manner and then changing the process.  These improvements should be the product of lessons learned data, findings of audits, and process metrics collected and fed back into the processes.

The software development process described in this SDP generally follows MIL-STD-498.  Where a process described in the SDP is deemed to be inadequate, cumbersome or non-responsive, any XY Project team member may submit a recommendation to change or improve that process.

When compliance with specific software policies, processes, forms, or templates would impose severe impacts on project cost, schedule, resources, or customer relations, the implementing developer may request a waiver/deviation of specific provisions.  They must propose reasonable and detailed alternatives during project planning.  Requests for waivers/deviations must cite specific provisions of policies, processes, forms, or templates for which waivers/deviations are being requested, the impact of compliance, and alternatives to be implemented by the XY project.

The Software Engineering Process Group (SEPG), interfacing with  the SSC San Diego SEPO,  shall be responsible for evaluating and acting upon suggestions for improvements in policies, processes, procedures, waivers/deviations, and standard forms and templates referenced in this SDP.  In addition, process metrics collected during program development and lessons learned from this and other projects will be used to update the XY Project processes.  The Software Project Manager  is authorized to approve SEPG recommended changes to the XY Project processes described in the SDP.

[End Sample]

### Other Activities

[Sample]

This paragraph has been tailored out as all software development activities needing to be addressed have been covered in other paragraphs of this document.

[End Sample]

This page intentionally left blank

# SCHEDULES AND ACTIVITY NETWORK

Guidance

This section shall present:

- Schedule(s) identifying the activities in each build and showing initiation of each activity, availability of draft and final deliverables and other milestones, and completion of each activity

- An activity network, depicting sequential relationships and dependencies among activities and identifying those activities that impose the greatest time restrictions on the project.  Activity networks can be easily created by using project management tools such as Microsoft Project.

This is also a good section to put your project’s Work Breakdown Structure (WBS).   An example WBS is shown below.

Project XY WBS				COST	  EFFORT  SCHEDULE   RISK*  POC

$	  #hrs.        # montths/weeks      Point of contact

1.0 Project XY

1.1 Project Management

1.1.1 Project Planning

1.1.2 Project Tracking and Control

1.1.2.1 Metrics Collection and Analysis

1.1.3 Cost Estimation

1.1.4 Contracts (Acquisition and Monitoring)

1.1.5 Travel

1.1.6 Training (internal)

1.1.7 Risk Management

1.1.8 Reviews

1.1.8.1 Technical

1.1.8.2 Management

1.2 Systems Engineering

1.2.1 Requirements Analysis

1.2.2 Computer Security

1.3 Software Engineering

1.3.1 Software Requirements Analysis

1.3.2 Software Design

1.3.3 Coding and Unit Testing

1.3.4 CSCI Testing

1.3.5 Software Tools and Compilers

1.4 Hardware Engineering

1.4.1 Design

1.4.2 Procurement

1.5 Facilities

1.5.1 Physical Security

1.5.2 Facilities Management

1.6 Integrated Logistics Support

1.6.1 Documentation

1.6.2 Training

1.6.3 Spare Parts

1.7 System Level Testing

1.7.1 Integration Testing

1.8 Software Configuration Management

1.8.1 Configuration Identification

1.8.2 Configuration Control

1.8.3 CCB

1.9 SQA

1.9.1 Audits

1.9.2 Requirements Traceability

* Risk column should identify what the major risk is for that WBS element.

# PROJECT ORGANIZATION AND RESOURCES

Guidance

This section shall be divided into the following paragraphs to describe the project organization and resources to be applied in each build.

[Sample]

The XY Project  and related organizations are  described in paragraph 7.1.

[End Sample]

## PROJECT ORGANIZATION

Guidance

This paragraph shall describe the organizational structure to be used on the project, including the organizations involved, their relationships to one another, and the authority and responsibility of each organization for carrying out required activities.  Below is an example organization chart for Project XY.

[Sample]

[End Sample]

[Notes]

| Roles | Comments |
| --- | --- |
| Sponsor | OPNAV level organization providing Mission Element Need Statement (MENS) and DoN budget. |
| Program Office | SYSCOM level organization tasked by OPNAV to perform system acquisition to meet MENS. |
| Program Manager | SYSCOM level manager, assigned responsibility to direct system acquisition (hardware/software). |
| Configuration Control Agent | SYSCOM level manager responsible for overall system configuration. |
| System CCB | SYSCOM level configuration control board controlling the system configuration (hardware/software) a.k.a. SCCB. |
| Project | A major component of a Program, can be either a hardware or software configuration item. |
| System Test Organization | Organizational entity charged with system level acceptance testing. May, or may not, be at a separate geographic location but definitely has a separate chain of command. |
| System Test Manager | Office within the System Test Organization charged with responsibility for system testing. |
| System Test Group | Collective name of system test staff. |
| System Test Engineer | An individual on the System Test Group. |
| Project Manager | In our example a SYSCOM level manager responsible to the Program Manager for a project, both hardware and software configuration items. However, it should be noted that this responsibility may also be placed within an organization such as SSC San Diego. |
| Systems Engineering Manager | Manager responsible to the Program Manager for the overall system engineering. A candidate for the role of System CCB Chairperson. |
| Systems Engineering Group | System level engineering staff, responsible for the system configuration (hardware/software) and the production and maintenance of the System Specification (i.e., SSS). |
| Systems Engineer | Member of the Systems Engineering Group. |
| Systems Engineering Requirements Team | Member of the Systems Engineering Group charged with specific responsibilities for managing the system requirement’s database. |
| Software Development/Maintenance Organization | Organizational entity, such as SSC San Diego, charged with system software development/maintenance. |
| Senior Management | A senior manager (i.e., Executive Director, Department Head, or possibly a Division Head) providing infrastructure resources (i.e., facilities, admin., contracting, supply) to support an internal entity as a Software Development/Maintenance Organization. |
| Software Engineering Process Office | SSC San Diego’s senior level entity providing process improvement direction. |
| Software Engineering Process Group | Professional staff providing Software Process Improvement (SPI) leadership to an SSC San Diego internal organization, such as a Division. |
| Software Project Manager | An SSC San Diego ‘manager’ (i.e., a Division Head, or possibly Branch Head) responsible to the Project Manager for assigned software CSCIs. A candidate for CCB chairperson. |
| Software Development Manager | An organizational line manager (i.e., a branch head or group leader), responsible for software development to the Software Project Manager. |
| Software Development Group | Collective name of the software engineering staff responsible for CSCI development. |
| Software Design Team | Staff responsible for software architecture and design. |
| Software Production Team | Staff responsible for code, and/or reuse component selection, and unit test. |
| Software Requirements Team | Staff responsible for the software requirement’s database. |
| Software Test and Evaluation Manager | An organizational line manager (i.e., a branch head or group leader) responsible for CSCI and Integration Test and Evaluation to the Software Project Manager. |
| Software Test and Evaluation Group | Collective name of the software engineering staff responsible for CSCI integration and testing. |
| CSCI Test Team | Software engineering staff responsible for Internal CSCI Testing. |
| Integration Test Team | Software engineering staff responsible for Internal CSCI/HWCI Testing. |
| Delivery Team | Software engineering staff responsible for on site deliveries, training, and testing. |
| SCM Manager | An organizational line manager (i.e., a branch head or group leader) responsible for Software Configuration Management (SCM) to the Software Project Manager. |
| SCM Group | Collective name of the software engineering staff responsible for SCM functions. |
| Documentation Team | Staff responsible for production and maintenance of project documentation, such as software specifications (i.e., SRS) and users manuals. |
| Librarian | Member of engineering staff who is keeper of document and program baselines (check in/out) |
| SQA Manager | An organizational line manager (i.e., a branch head or group leader), responsible for Software Quality Assurance (SQA) functions who reports to the Software Project Manager. |
| SQA Group | Collective name of the software engineering staff responsible for SQA functions. |
| IV&V Organization | Program Level organization charged with the responsibility of providing resources and management for IV&V functions. Most often organized such that they report to the Program Manager, typically an organizational entity with a chain of command separate from SSC San Diego’s. |
| IV&V Manager | Office within the IV&V Organization charged with responsibility for IV&V functions. |
| IV&V Group | Collective name of IV&V staff. |

[End Notes]

## PROJECT RESOURCES

Guidance

This paragraph shall describe the resources to be applied to the project. It shall include, as applicable:

a. Personnel resources, including:

1)  The estimated staff-loading for the project (number of personnel over time)

2)  The breakdown of the staff-loading numbers by responsibility (for example, management, software engineering, software testing, software configuration management, software product evaluation, software quality assurance)

3)  A breakdown of the skill levels, geographic locations, and security clearances of personnel performing each responsibility

b. Overview of developer facilities to be used, including geographic locations in which the work will be performed, facilities to be used, and secure areas and other features of the facilities as applicable to the contracted effort.

c. Acquirer-furnished equipment, software, services, documentation, data, and facilities required for the contracted effort. A schedule detailing when these items will be needed shall also be included.

d. Other required resources, including a plan for obtaining the resources, dates needed, and availability of each resource item.

An example of a staffing plan is given in Table 7-1.

[Sample]

Table 7-1 Personnel Requirements (Person yrs)

| Activity Personnel | System Rqmts Analysis/Design | Detailed Design | Code and Unit Test | System Integration | Subtotals |
| --- | --- | --- | --- | --- | --- |
| Management | 1 | 2 | 2 | 1 | 6 |
| Systems Engineer | 5 | 3 | 2 | 1 | 11 |
| Hardware | 3 | 2 | 2 | 1 | 8 |
| S/W Engineer | 5 | 10 | 15 | 3 | 33 |
| CM | 2 | 2 | 4 | 2 | 10 |
| SQA | 1 | 1 | 2 | 1 | 5 |
| Testing | 1 | 2 | 1 | 5 | 9 |
| IV&V | 1 | 2 | 2 | 4 | 9 |
| Facilities | 1 | 1 | 2 | 2 | 6 |
| ILS | 1 | 1 | 2 | 2 | 6 |
| Subtotals | 21 | 26 | 34 | 22 | (Total) 103 |

[End Sample]

# NOTES

Guidance

This section shall contain any general information that aids in understanding this document (e.g., background information, glossary, and rationale). This section shall include an alphabetical listing of all acronyms, abbreviations, and their meanings as used in this document and a list of any terms and definitions needed to understand this document.

## ACRONYMS

Guidance

Alphabetically list  all acronyms used in this document.

[Sample]

LIST OF ACRONYMS

AIS		Automated Information System

AWG		Architecture Working Group

CAPM		Contractor Acquisition and Performance Monitoring

CASE 		Computer-Aided Software Engineering

CC		Configuration Control

CDRL		Contract Data Requirements List

CI		Configuration Item

CM		Configuration Management

CMM		Capability Maturity Model

COM		Computer Operation Manual

COTS		Commercial Off-the-Shelf

CPM 		Computer Programming Manual

CR 		Change Report

CSAR		Configuration Status Accounting Report

CSCI		Computer Software Configuration Item

DBDD		Database Design Description

DCR		Document Change Request

DDR		Detailed Design Review

DID		Data Item Description

DoD 		Department of Defense

DoDI 		Department of Defense Instruction

DoN		Department of Navy

ECP		Engineering Change Proposal

FOT		Functional Operability Testing

FQT		Formal Qualification Test

FSM 		Firmware Support Manual

FST		Functional Stress Testing

HWCI	 	Hardware Configuration Item

IDD		Interface Design Description

IEEE		Institute of Electronics and Electrical Engineers

ILS		Integrated Logistics Support

IMT		Interface Message Tests

IRS		Interface Requirements Specification

IRT		Interface Recovery Tests

IST		Interface Stress Tests

IVT		Interface Validation Tests

IV&V 		Independent Verification and Validation

KPA		Key Process Area

LCCB		Local Software Configuration Control Board

LCM		Life Cycle Maintenance

MENS		Mission Element Needs Statement

MTP		Master Test Plan

NDI		Non-Developmental Item

OCD 		Operational Concept Description

OOD		Object-Oriented Design

OPEVAL	Operational Evaluation

PAT		Program Acceptance Test

PP		Program Package

PR		Problem Report

PSM		Practical Software Measurement

PTR		Program Trouble Report

QA		Quality Assurance

RAM		Reuse Adaptation and Management

RM		Requirements Management

R&R		Review and Response

RT		Regression Test

SCCB		System Configuration Control Board

SCM		Software Configuration Management

SCMP		Software Configuration Management Plan

SCOM		Software Center Operator Manual

SDD 		Software Design Description

SDF		Software Development File

SDL 		Software Development Library

SDP 		Software Development Plan

SEE 		Software Engineering Environment

SEI		Software Engineering Institute

SEN		Software Engineering Notebook

SEPG		Software Engineering Process Group

SEPO		Software Engineering Process Office

SIOM 		Software Input/Output Manual

SIP 		Software Installation Plan

SOW 		Statement of Work

SPE		Software Product Evaluation

SPI		Software Process Improvement

SPIP		Software Process Improvement Plan

SPM		Software Project Manager

SPP		Software Project Planning

SPS 		Software Product Specification

SPTO		Software Project Tracking and Oversight

SQA		Software Quality Assurance

SQAP		Software Quality Assurance Plan

SQER		Software Quality Evaluation Report

SQT		System Qualification Test

SRS 		Software Requirements Specification

SSC		SPAWAR Systems Center San Diego

SSDD 		System/Subsystem Design Description

SSS 		System/Subsystem Specification

STD 		Software Test Description

STE		Software Test Environment

STP 		Software Test Plan

STR 		Software Test Report

STrP 		Software Transition Plan

SU		Software Unit

SUM 		Software User Manual

SVD 		Software Version Description

SW 		Software

SYSCOM	System Command

TECHEVAL	Technical Evaluation

TRR		Test Readiness Review

WBS 		Work Breakdown Structure

[End Sample]

This page intentionally left blank

# APPENDIX A

Guidance

Appendices may be used to provide information published separately for convenience in document maintenance (e.g., charts and classified data).  As applicable, each appendix shall be referenced in the main body of the document where the data would normally have been provided. Appendices may be bound as separate documents for ease in handling.  Appendixes shall be lettered alphabetically (A, B, C…).