Software Project Planning

Process

VERSION 1.2

September 8, 1997

Software Engineering Process Office (SEPO), D13

Space and Naval Warfare Systems Center, San Diego

53560 Hull Street

San Diego CA 92152-5001

Approved for public release; distribution is unlimited.

THIS PAGE INTENTIONALLY LEFT BLANK

Software Project Planning

Process

VERSION 1.2

September 8 , 1997

SPACE AND NAVAL WARFARE SYSTEMS CENTER, SAN DIEGO

SOFTWARE ENGINEERING PROCESS OFFICE, D13

Developed By:  Brian Groarke and George Robertson

THIS PAGE INTENTIONALLY LEFT BLANK

Administrative Information

This document is to be used  as guidance for use by Software Project Managers  at the Space and Naval Warfare Systems Center, San Diego hereinafter referred to as SSC San Diego.  SEPO assumes responsibility for this document and updates it as required to meet the needs of users within SSC San Diego.  SEPO welcomes and solicits feedback from users of this document so that future revisions of this document will reflect improvements, based on organizational experience and lessons learned.  SEPO provides copies of this document to students attending SEPO training courses and workshops as well as copies upon request to others in accordance with this document's distribution statement.

If you have any questions or comments regarding this document please feel free to communicate them via the Document Change Request (DCR) form located at the back of this document.

Approved for public release; distribution is unlimited.

Brian Groarke, SEPO, SSC San Diego D13

Voice:(619)553-6248, Fax:(619)553-6249, Internet: groarke@spawar.navy.mil

Preface

The purpose of the Software Project Planning (SPP) Process is to satisfy the requirements of the Level 2 Software Project Planning (SPP) Key Process Area of the Software Capability Maturity Model. Updates to this process will be made as comments are received from the users.  The flow diagram of this process is shown in Figure 1-1.   The SPP process requires the use of several other SSC San Diego processes, including the Requirements Management Guidebook, the Software Size, Cost and Schedule Estimation process, the Formal Inspection process, the Software Configuration Management process, the Software Project Tracking and Oversight process, the Contractor Acquisition and Performance Monitoring (CAPM) process, the Software Product Engineering (SPE) Implementation Guide, and the Software Quality Assurance process.

figure 1-1 SPP Process Flow Diagram

RECORD OF CHANGES

*A - ADDED  M - MODIFIED  D - DELETED

| CHANGE NUMBER | DATE | NUMBER OF FIGURE, TABLE OR PARAGRAPH | A* M D | TITLE OR BRIEF DESCRIPTION | CHANGE REQUEST NUMBER |
| --- | --- | --- | --- | --- | --- |
| V1.2 | 9/8 1997 | ALL | A M D | Various changes resulting from a formal inspection on this document | 1 |

TABLE OF CONTENTS

Section	 										Page

1. INTRODUCTION

1.1 PURPOSE

1.2 BACKGROUND

1.3 SCOPE

1.4 DOCUMENT OVERVIEW

1.5 PROCESS OVERVIEW

1.5.1 PLANNING INITIATION

1.5.2 DEVELOP SDP

1.5.3 REVIEW AND APPROVE SDP

1.5.4 IMPLEMENT SDP PROCESSES AND APPLY SPTO PROCESS

1.5.5 PROCESS MEASUREMENT AND IMPROVEMENT

1.5.6 REVISE SDP

1.6 REFERENCE DOCUMENTS

1.7 ACRONYMS AND TERMS

2. PROJECT PLANNING PROCESS DEFINITION

2.1 PLANNING INITIATION

2.1.1 PURPOSE

2.1.2 ROLE AND RESPONSIBILITY

2.1.3 ENTRY CRITERIA

2.1.4 INPUT

2.1.5 PROCESS ACTIVITY

2.1.6 OUTPUT

2.1.7 EXIT CRITERIA

2.1.8 PROCESS METRICS

2.2 DEVELOP SDP

2.2.1 PURPOSE

2.2.2 ROLE AND RESPONSIBILITY

2.2.3 ENTRY CRITERIA

2.2.4 INPUT

2.2.5 PROCESS ACTIVITY

2.2.6 OUTPUT

2.2.7 EXIT CRITERIA

2.2.8 PROCESS METRICS

2.3 REVIEW AND APPROVE THE SDP

2.3.1 PURPOSE

2.3.2 ROLE AND RESPONSIBILITY

2.3.3 ENTRY CRITERIA

2.3.4 INPUT

2.3.5 PROCESS ACTIVITY

2.3.6 OUTPUT

2.3.7 EXIT CRITERIA

2.3.8 PROCESS METRICS

2.4 IMPLEMENT SDP AND APPLY SOFTWARE PROJECT TRACKING AND OVERSIGHT (SPTO) PROCESSES

2.4.1 PURPOSE

2.4.2 ROLE AND RESPONSIBILITY

2.4.3 ENTRY CRITERIA

2.4.4 INPUT

2.4.5 PROCESS ACTIVITY

2.4.6 OUTPUT

2.4.7 EXIT CRITERIA

2.4.8 PROCESS METRICS

2.5 PROCESS MEASUREMENT AND IMPROVEMENT

2.5.1 PURPOSE

2.5.2 ROLE AND RESPONSIBILITY

2.5.3 ENTRY CRITERIA

2.5.4 INPUT

2.5.5 PROCESS ACTIVITY

2.5.6 OUTPUT

2.5.7 EXIT CRITERIA

2.5.8 PROCESS METRICS

2.6 REVISE SDP

2.6.1 PURPOSE

2.6.2 ROLE AND RESPONSIBILITY

2.6.3 ENTRY CRITERIA

2.6.4 INPUT

2.6.5 PROCESS ACTIVITY

2.6.6 OUTPUT

2.6.7 EXIT CRITERIA

2.6.8 PROCESS METRICS

3. PROJECT PLANNING AIDES

3.1 PROJECT MANAGEMENT TOOLS

3.2 HOW SEPO CAN HELP

4. DOCUMENT CHANGE REQUEST (DCR)	DCR-

List of figures

Figure	Page

figure 1-1	vii

figure 2-1 .......................................................................................................................................2-1

# INTRODUCTION

## Purpose

The purpose of this document is to describe the processes, procedures, and guidelines that should be followed by a software project manager in order to plan and execute a productive and successful project. It is assumed that the reader is familiar with the SSC San Diego organizational policy for Software Project Planning (SPP).

## Background

Software project planning is a Level 2 Capability Maturity Model (CMM) Key Process Area (KPA).   Satisfying this KPA is a major step toward achieving Level 2 (Repeatable).  This KPA requires a written process for planning a software project.  It also requires the development of a project  Software Development Plan (SDP), which is the document which describes the plan for the software project.  The planning phase is one of the most crucial steps in any software development project.  The success of a software project is often determined in the planning phase.  Lack of adequate planning often results in a project’s failure to meet either cost, schedule, or performance objectives or all three. The quality of your project plan will probably reflect the quality of  your project. Be thorough, concise and precise. It is never too early to plan.

## Scope

This process applies to any software project at SSC San Diego and also to any activity of the software development life cycle.  Though this process is written from the viewpoint of a project in the requirements activity, it can be easily modified for use by projects in any activity of the software life cycle.  Even software projects that are in life cycle maintenance can implement this process for planning software builds or for implementing Engineering Change Proposals (ECPs).

## Document Overview

This document addresses steps and guidelines for performing software development planning on a software project.   Section 1 provides background and process overview information.  Section 2 provides detailed information on each step of the process.  Section 3 provides information on software project planning aides.  The following provides the format and the format definitions used to describe each of the process steps in Section 2 of the SPP Process.

PURPOSE: The objective of the process activity.  If a subprocess activity exists, the details are described in that specific paragraph description.

ROLE AND RESPONSIBILITY: The responsibilities of individuals or groups for accomplishing a process activity.

ENTRY CRITERIA: The elements and conditions necessary to be in place to begin a process activity.  Reading lower level activities assumes that the entry criteria for all higher level activities have been satisfied.

INPUT: Data or material with which a process activity is performed.

PROCESS ACTIVITY: Actions to transform an input, as influenced by controls, into a predetermined output.

OUTPUT: Data or material produced by or resulting from a process activity.  It must include the input data in some form.  The output title differs from the input title in order to indicate that an activity has been performed.

EXIT CRITERIA: Elements and/or conditions necessary to be in place to complete a process activity.

PROCESS METRICS: Data collected which can be analyzed and used to improve the process.

## Process Overview

### Planning Initiation

The SSC San Diego Software Project Planning (SPP) process begins with the planning initiation step. In this step a software project manager is selected and resources and budget are allocated to the planning and replanning activities. The Requirements Management (RM) Guidebook is an interfacing process to the SPP process.  Requirements are the major driving force in SPP and therefore are a major interface to this process.  Without requirements, you would not know what to plan or what to estimate. Initial software estimates and software activities are also developed in this step.  The SSC San Diego Software Size, Cost, and Schedule Estimation process is an interfacing process.

### Develop Sdp

The next step in the process is to develop the Software Development Plan (SDP).  The MIL-STD-498 Data Item Description (DID) for the SDP, DI-IPSC-81427,  should be used as a format for the SDP.  The SSC San Diego SDP template, which is based on the MIL-STD-498 DID, can be used as a guide for developing the project specific SDP.  The SDP should include items such as software estimates, schedules, milestones, Work Breakdown Structure (WBS), software development environment, software development methodology, software test methodology, and software risks.  The SDP is used to establish commitments on the project.  Software estimates are refined using the SSC San Diego Software Size, Cost, and Schedule Estimation process.

### review and approve sdp

After the SDP has been developed it should undergo formal review and approval.  The SSC San Diego Formal Inspection process is one type of review methodology that can be used.   Review of the SDP should include all groups internal and external to the organization which will be affected by the work in the SDP.  Affected groups, both internal and external to the organization, should also approve the SDP by signing the signature page of the SDP indicating their commitment and acceptance of the SDP.

After the SDP has been approved it should be placed under configuration management.  The SSC San Diego Software Configuration Management (SCM) process can be used as a guide to develop the project’s SCM process.

### Implement SDp processes and apply spto process

The project is now ready to implement the activities as described in the SDP.  In implementing the SDP, follow the project’s tailored version of the SSC San Diego Software Project Tracking and Oversight (SPTO) process to provide information about the software project which can precipitate changes to the SDP.  These changes should be implemented in accordance with the project’s SCM  process.  The project should also implement the project’s tailored SQA process in order to monitor the project’s software development activities.  In addition, the SQA group should be monitoring the activities of the SPP process.

### Process measurement and improvement

Metrics are collected on each process step and are then used to develop process improvements in the SPP process.  These measurements are analyzed against both planned and historical data, if available.

### revise sdp

Proposed changes to the SDP are analyzed and approved changes are implemented.  After changes are made, the SDP should follow the project’s standard review and approval process.

## Reference Documents

- Requirements Management Guidebook

- SSC San Diego Size, Cost, and Schedule Estimation Process

- SSC San Diego Software Configuration Management Process

- SSC San Diego Formal Inspection Process

- SSC San Diego Software Project Tracking and Oversight Process

- SSC San Diego Software Quality Assurance Process

- SSC San Diego SDP Template

- SSC San Diego Reuse Adaptation and Management (RAM) Process

- SSC San Diego Risk Management Process

- SSC San Diego Software Management for Executives Guidebook

- SSC San Diego Contractor Acquisition and Performance Monitoring (CAPM) Process

- MIL-STD-498  Software Development and Documentation, 5 December 1994

- Capability Maturity Model for Software V1.1

- NAWCAD Procedure for Preparing a Software Development Plan

## Acronyms and Terms

CAPM Contractor Acquisition and Performance Monitoring

CM	Configuration Management

CMM	Capability Maturity Model

DCR	Document Change Request

DID	Data Item Description

ECP	Engineering Change Proposal

KPA	Key Process Area

PR/CR	Problem Report/Change Request

RM	Requirements Management

SCM	Software Configuration Management

SDP	Software Development Plan

SEPO	Software Engineering Process Office

SOW	Statement of Work

SSC San Diego Space and Naval Warfare Systems Center, San Diego

SPM	Software Project Manager

SPE	Software Product Engineering

SPP	Software Project Planning

SPTO	Software Project Tracking and Oversight

SQA	Software Quality Assurance

SQAP  Software Quality Assurance Plan

SSM	Software Subcontractor Management

WBS	Work Breakdown Structure

Project Manager - person responsible for planning and execution of the project, both hardware and software.

Software Project Manager (SPM) - person responsible for the planning and execution of the software portion of a project.

Sponsor/Customer - the acquirer of the system being developed.  The source of the funding for the

project.

# Project planning process definition

This section describes each of the process steps as depicted in Figure 2-1.

process activity			task				       outputs

Initial Planning Data & Role Assignments

Review SOW and identify initial product requirements Planning Initiation - Make initial estimate of cost, resources, space requirements - Assign key project leadership positions - Identify project initial risks and constraints

Define planning group assignments MS Project Plan; Draft SDP Develop SDP - Planning group reviews SDP Template (guidance & sample) - Analyze planning issues and refine estimates - Tailor SDP template into a project SDP

Perform rigorous technical review with project stakeholders Final SDP; Final MS Project Plan; Baseline SDP; Document Inspection report; Standard process PR/CRs Review and Approve SDP - Resolve issues and update Draft to incorporate comments - Gain formal commitment to SDP - CM Group places SDP under CM control in project library - Change requests and/or new process definitions developed during SDP production submitted to SEPO

Implement SDP Processes and Apply SPTO Process

Periodic interactive technical reviews schedule; Products resulting from the executed SDP - Implement project measurements program - Implement SQA activities and Review SQA reports - Implement project tracking and oversight functions - Assess metrics on cost performance to determine if any changes to plans and /or SDP are required - Implement SPE KPA and SSM KPA

Process data; Replanning data; Org, Project, and SPP Process PR/CRs Process Measurement and Performance

- Analyze selected standard process performance - Analyze project unique process performance - Develop proposed process improvements - Gain commitment for proposed changes

SDP PR/CRs; Next revision of the SDP Revise SDP - Determine if process improvement required for SDP - Determine impact of project replanning on SDP

Figure 2-1.  Project Planning Process

## Planning Initiation

### PURPOSE

The purpose of this process step is ensure that the necessary requirements have been met in order to properly carry out the planning activities.

### ROLE AND RESPONSIBILITY

The project manager is responsible for carrying out this process step.

### ENTRY CRITERIA

a.   A Software Project Manager is designated to be responsible for developing software size, cost, schedule, and resource estimates; preparing project planning documents; and negotiating commitments.

b.  Those responsible for preparing the project planning documents are skilled or have received training in software project planning and software estimating.

c.  The Statement of Work (SOW)  or tasking statement has been documented.  The SOW or task statement should include the scope of the work, technical goals and objectives, identification of customers and end users, imposed standards, assigned responsibilities, cost and schedule constraints and goals, dependencies between the software project and other organizations, resource constraints and goals, and other constraints and goals for development and/or maintenance.

d.	Initial allocated requirements have been documented.

e.   Adequate resources and budget for software project planning have been identified and allocated. Adequate budget generally means 1-2% of the software project budget.

f.   Customer/sponsor required documentation (e.g. Computer Resources Life Cycle Management Plan, Software Support Requirements Analysis, Transition Plan, Acquisition Plan, etc.) is available and complete.

g. SSC San Diego Software Project Planning Policy has been reviewed.

### INPUT

Planning budget and trained personnel.

SSC San Diego Software Project Planning Policy.

Project’s documented software requirements.

Documented SOW or tasking statement.

### PROCESS ACTIVITY

There are two major activities to initiating software project planning: develop estimates, and plan software activities.

a.  Develop Estimates

(1) Review the “SSC San Diego Software Project Tracking and Oversight Process” document  to determine the measurement data to be collected for project tracking and oversight.

(2) Review the statement of work and the initial allocated requirements to scope the effort.

(3) Make initial estimates of software size, cost and schedule using the " SSC San Diego Software Size, Cost, and Schedule Estimation Process” document.

(4) Estimate the project's critical computer resources.  Critical computer resources may be in the host environment, in the integration and testing environment, in the target environment, or in any combination of these.

(5) Estimate the space requirements for the project's software engineering facilities and make a preliminary identification of  the hardware, support tools and associated costs (e.g., license fees, maintenance cost) required for the target environment, the host environment and the integration and test environment.

b.  Plan Software Activities

(1)  Perform an initial assessment of the following:

(a)  Software objectives, allocated requirements and interface requirements.  The “Requirements Management Guidebook” available for downloading from the SEPO Home page will assist in this step.

(b)  Customer delivery schedule requirements.

(c)  Customer budget limitations.

(d)  System technical constraints.

(e)   Staffing constraints (in-house and contractors).

(f)   Contracting needs.

(g)   Resource constraints.

(h)   Software development environment.

(i)    Software processes to be used.

(j)    Design, programming, software engineering and test requirements and  standards.

(k)   Configuration management requirements.

(l)    Quality assurance requirements.

(m)  Non-deliverable software and hardware requirements.

(n)   Risks and risk reduction strategies for the project.

(o)   Documentation requirements.

### OUTPUT

Initial planning data including a Project budget and/or WBS that includes a line item for the SPP task and the project organization chart identifies the project’s Software Project Manager (SPM).

### EXIT CRITERIA

A Project Software Manager for the project has been identified.  Adequate resources, funding have been allocated to perform the planning task, and an initial understanding of the scope of the effort has been accomplished.

### PROCESS METRICS

Effort expended in planning work efforts.

## Develop SDP

### PURPOSE

The purpose of this process step is to develop the Software Development Plan (SDP) for the project. The SDP  is the document that allows the customer  insight into all stages of the software development process and addresses the commitments  of the software developer to the allocated requirements.  It identifies resources, estimates of size and cost, schedules, constraints, capabilities of the software developer's organization and identifies the products to be delivered.  The plan identifies a basis for managing, for tracking the software activities, and a means for communicating status of the software development tasks.  The plan documents each group's responsibility for the development of the software.  The organization’s standard software processes are a major input to the SDP.

### ROLE AND RESPONSIBILITY

The Software Project Manager (SPM), or whomever the SPM designates to develop the SDP,  is responsible to lead  the development effort for the SDP.

### ENTRY CRITERIA

a.  The Software Project Manager has been designated and is responsible for the creation of the SDP.

b.  The initial software size, cost, schedule and resource estimates have been developed.

c.  Adequate resources and budget for project planning have been identified and allocated.

d.  The software quality assurance and configuration management task leaders have been identified and assigned to the project planning group.

e.  The project planning group has reviewed the initial planning data.

### INPUT

Initial planning data.

The organization’s standard software processes (e.g. SCM process, SQA Process, etc.)

### PROCESS ACTIVITY

a.  The planning group has downloaded the SDP Template from the SEPO Home page and familiarized themselves with the guidance information and samples contained in the template.  Tailoring the SDP template will require that the planning group address the following items:

(1) Scope/Objective/Goals - Define the project's purpose, the customer, the scope of the project to bound the project, the project's goals and objectives, the product delivery date and criteria for determining the project's success.

(2) Requirements - Identify the data base of requirements allocated to software, the functional requirements which the allocated requirements support and a high level summary of the entire project.

(3) Project Organization - Identify the project's organizational structure and define the relationship among the organizational elements.  Identify for each organizational element its authority and responsibility for each major task area.

(4) Task Definition - Refine the major tasks to develop the software (e.g., software design, software test, independent verification and validation).  This can be accomplished using a work breakdown structure format.

(5) Schedule - Refine the project's overall schedule and schedules associated with each task including significant events (reviews, audits, key meetings) related to the task and interdependencies with other tasks.

(6) Cost - Refine the cost for the software product, contracting efforts, quality assurance efforts, configuration management efforts, training expense, software development environment, software test environment, software licenses and travel expenses.  The cost should be expressed as a total cost throughout the life of the project and as yearly cost for multi-year projects.  Refer to the " SSC San Diego Software Size, Cost and Schedule Estimation Process" document for procedures to develop the cost.

(7) Resource Requirements – Refine any human resources, software resources and hardware resources and any limiting factors associated with each resource (e.g., dates available, skill type, sequences of events and dependencies).

(a) Human Resources - Identify the human resources by skill type (management,  software engineering, testing, configuration management, quality assurance) assigned to each task in the project's schedule.  Indicate the chronological time and duration when the resources are required.

(b) Software Resources - Identify the software resources that are necessary for the project, the provider of the software (e.g., government furnished, commercial off the shelf, non-developmental item, new development), and the need dates.

(c) Hardware Resources - Identify the equipment that is necessary for the project, the provider of the equipment (e.g., government furnished, contractor furnished, commercial), procurement agreement (purchase, rental, existing) and the need dates.

(d) Critical Computer Resources - Identify any critical computer resource (i.e., memory, throughput, I/O) that will impact any task within the project.

(8) Software Process - Identify the techniques, methodologies and tools for the development and control of the software through all its development phases (e.g., preliminary design, detailed design, implementation, integration, testing, internal/external reviews, inspections, corrective action process, problem/change reports, software product evaluation).

(9) Software Standards - Identify the standards and procedures that will be used for design and implementation of the software product(s) including language specific standards, the contents and maintenance of the software development files.

(10) Software Development Environment/Software Test Environment - Identify the software development environment and software test environment.  Address their performance requirements.  Identify any custom tailoring of the environments that are needed for the project and the schedule for the environments including dates of installation, date of availability, need date and duration.  Include any maintenance requirements for the environments.

(11) Software Licenses - Identify all software license agreements associated with the software development environment, software test environment, target environment, maintenance environment and the delivery of the product and associated software package to the customer.  Determine the approach the project will use for each licensed item and maintenance agreement for each licensed item.

(12) Documentation - Identify the documentation standard or the format to be used to develop the project documentation.  Identify specific tailoring of documents, delivery medium, delivery schedule, document review cycle, project management reports and maintenance of documentation.

(13) Risk Analysis and Risk Reduction - Identify the risks in the software project by utilizing a risk analysis method which provides risk identification, risk factors, risk assessment, risk prioritization, risk management strategies, risk resolution, risk monitoring techniques and document the contingency procedures for each area of risk on the project.  Refer to the " SSC San Diego Risk Management Process" document.

(14) Training - Identify the required training needs and associated efforts (e.g., on the job training assignments) necessary for the staff in such areas as software methodology, tools, languages, and software packages. Also, identify the training requirements for the customer to effectively use the delivered software.

(15) Project Constraints - Identify the constraints that will impact meeting the customer's goals ( i.e., start date, completion date, specific tools, software development environment, software test environment, availability of tools or environments, resources, and dependencies on external activities relating to project commitments).

(16) Quality Assurance - Identify the organization's structure and personnel resources for performing the quality assurance activities on the software products produced for the customer and the QA activities for evaluating the software engineering or development processes.  Define the approach for evaluating the software and associated documentation, the software engineering processes, and identify the tools utilized by the SQA group.  Refer to “SSC San Diego Software Quality Assurance Process” document and associated SQA Plan template.

(17) Configuration Management - Identify the organization's structure and personnel resources for performing software configuration management for the software developed or used throughout the project.  Define the configuration control flow used for changes to software and documentation and deliveries of products.  Refer to the " SSC San Diego Software Configuration Management Process" document and associated templates for further details.

(18) Contracting Needs - Identify any technical agreement or contract that is needed by the project to meet its goal.  Define for each technical agreement or contract the end product to be procured or produced, type of agreement/contract, type of funding, funding expiration date, lead time for contract preparation, award date and cost.  Refer to the " SSC San Diego CAPM” process.

(19) Security - Identify the security levels of any facility used on the project.  Identify any classified processing or security issues associated with software items (e.g., tool), firmware and hardware.

c.  The SDP template is tailored, incorporating the findings of the planning group into a project specific draft Software Development Plan.

Note: At the early stages of a software project many sections of the SDP may include items that are “TBD” (To Be Determined).  This is quite normal and does not present a problem as long as those items are planned before their implementation.

### OUTPUT

Draft Software Development Plan.

### EXIT CRITERIA

Software Development Plan has been developed using the SSC San Diego SDP template.

### PROCESS METRICS

Effort expended planning and developing the SDP.

## Review and approve the SDP

### PURPOSE

The purpose of this process step is to identify and correct any defects or missing information  in the SDP.   The approval of the document will signify the signees commitment to the SDP.

### ROLE AND RESPONSIBILITY

Project manager, senior management, software project manager, program sponsor, project personnel, systems engineering, hardware engineering, system test, SCM, SQA, and other affected groups are responsible for reviewing and approving the SDP.

### ENTRY CRITERIA

Draft SDP has been developed.

### INPUT

Draft SDP.

### PROCESS ACTIVITY

a.  Perform a rigorous technical review of the SDP.   One example of such a review is the SSC San Diego Formal Inspection process.   The purpose of the review is to uncover any defects or missing information in the SDP.

b. Change requests and/or new process definitions developed during SDP production should be submitted to SEPO.

c.  Integrate and validate corrections to the SDP.

d.  Gain commitment to the SDP by following the appropriate document approval process for the organization.  This process should include the Project Manager, the Software Project Manager, the Project Sponsor, and other groups, internal and external to the organization,  who are affected by the SDP.  All software project commitments made to individuals and groups external to the organization should be reviewed by senior management.

e. The SDP is put under control using the same CM  procedures  as would be used with any other of the project’s software documents.

### OUTPUT

a.  Reviewed and approved SDP filed in project document library.

b.	Document inspection report filed in project document library.

c.  Management and software engineering team commitment to the SDP.

d.  Baselined SDP under CM control.

### EXIT CRITERIA

SDP has been reviewed.  Defects in the SDP have been corrected and appropriate individuals have committed to the approved the SDP.

### PROCESS METRICS

Effort expended reviewing, making corrections to, and approving the SDP.

Number and severity of defects found.

## Implement SDP and Apply Software Project Tracking and Oversight (SPTO) Processes

### PURPOSE

The purpose of this process step is to carry-out the tasks as detailed in the SDP.

### ROLE AND RESPONSIBILITY

Any project personnel who have a defined task in the SDP is responsible for carrying-out their role.

### ENTRY CRITERIA

SDP has been reviewed, approved, and placed under SCM control.

### INPUT

Baselined SDP

### PROCESS ACTIVITY

a.  The project personnel execute the tasks as described in the SDP, invoking the disciplines of the CMM SPE KPA to ensure quality product engineering.

b.  In addition, as part of management’s planning and monitoring process, the Software Project Tracking and Oversight (SPTO) processes are applied.

c.  The disciplines of the CMM KPA for SQA are applied via the Software Quality Assurance Plan (SQAP) or the processes documented in the SDP.  SQA should be performed on both the software development activities and the SPP process itself.  Review SQA reports.

d.  The disciplines of the CMM KPA for Software Subcontractor Management (SSM) are applied for sub-contractor work.

### OUTPUT

Products resulting from the executed SDP. Periodic interactive technical reviews schedule.

### EXIT CRITERIA

SDP is being executed and the work effort monitored and managed.

### PROCESS METRICS

As defined in the SDP and as required by organizational management policy and processes.

## Process Measurement and Improvement

### PURPOSE

The purpose of this process step is to collect metrics on each step of the process and use that data to improve the process.

### ROLE AND RESPONSIBILITY

Software project manager or the person designated by the SPM to monitor and improve the SPP process.

### ENTRY CRITERIA

Metrics data collected from the software engineering and management process activities.

### INPUT

Metrics data base, change proposals (including feedback from process users), and problem reports affecting project, organization, and the SPP process.

### PROCESS ACTIVITY

a.  Analyze process metrics, change requests, and problem reports to determine process changes.  Compare metrics data to planned and historical data.  Investigate variances that exceed the project-specified thresholds.  Investigate cause of the variance.  If the tasks in the process itself are found to be the cause of the variance, then formulate proposed process changes.

b.  Draft process improvements for organizational standards, those specific to the project (i.e., tailored organizational standards or project unique), and to the SPP process.

e.  Gain commitment from the software engineering team (i.e., Inter-group Coordination) on the proposed process changes.

### OUTPUT

Team approved process improvement proposals for the organizational standards, the project process contained in the SDP, and the SPP process.  Process data and replanning data.

### EXIT CRITERIA

Process metrics have been analyzed and proposed process improvements have been drafted.

### PROCESS METRICS

Effort expended analyzing metrics and planning process improvements.

## REVISE SDP

### PURPOSE

The purpose of the process step is to ensure that the SDP remains current.

### ROLE AND RESPONSIBILITY

The Project Software Manager, or the person designated by the SPM, is responsible for updating the SDP.

### ENTRY CRITERIA

SDP, SCM, SQA, and SPTO process are being executed, results analyzed, and process improvement proposals drafted.

### INPUT

Metrics from the SPTO process; proposed process changes; and, changes in project plans as directed by the program sponsor.

### PROCESS ACTIVITY

a.  Analyze impact of directed project changes, such as changes in project schedules, resources, etc., as negotiated with the program sponsor.

b.  Incorporate approved changes into draft of next revision to the  SDP.

c.  Proceed to step 2.3 above.  The SCM process for updating the SDP should be the same as for any of the other project documentation.

### OUTPUT

a.  Next revision to the SDP.

b.  Change proposals or problem reports against organizational standard processes forwarded to the appropriate group responsible for the configuration control of organizational standard processes (i.e., Software Engineering Process Group).

### EXIT CRITERIA

SDP has been revised based on  data from the process analysis and programmatic changes affecting the project plans.

### PROCESS METRICS

Effort expended updating the SDP.

THIS PAGE INTENTIONALLY LEFT BLANK

# Project planning aides

## Project Management ToolS

Project management tools are an invaluable resource to software project managers.  They can automate many of the planning tasks of the SPM.

Project management tools can:

- Help you create a comprehensive plan

-  Define project schedule and budgetary goals

-  Define areas of responsibility

-  Schedules for high level tasks down to great detail

-  Establish task sequences

-  Define major/minor milestones

-  Assign resources to tasks

-  Calculate project budget on task-by-task basis

•  Most project management tools produce

-  Activity networks

-  Gantt charts

-  Calendars

-  Workhours forms

-  Status report forms

• Automated Tools

-  MacProject, SuperProject, Microsoft Project

Caution: Project management tools can sometimes be overwhelming.  Don’t over use them or you will be spending more time tracking and planning than actually doing work!

- Books

-  ‘A Manager’s Guide to Software Engineering’, R. Pressman, McGraw Hill, 1993

## How SEPO can help

Projects may contact SEPO for assistance in understanding and  implementing this process.  SEPO will also assist projects in tailoring the SDP template to their specific project needs.

THIS PAGE INTENTIONALLY LEFT BLANK

# DOCUMENT CHANGE REQUEST (DCR)

| Document Title: | Tracking Number: |
| --- | --- |
| Name of Submitting Organization: |  |
| Organization Contact: | Phone: |
| Mailing Address: |  |
| Short Title: | Date: |
| Change Location: (use section #, figure #, table #, etc.) |  |
| Proposed change: |  |
| Rational for Change: |  |
| Note: For the Software Engineering Process Office (SEPO) to take appropriate action on a change request, please provide a clear description of the recommended change along with supporting rationale. Send to: Commanding Officer, Space and Naval Warfare Systems Center, D13, 53560 Hull Street, San Diego, CA 92152-5001 or Fax to: (619)553-6249 or Email to: sepo.spawar.navy.mil DCR Form 9/1997 |  |